## GNR-D_Blue_Eval_report_0004.D77
TCD_ID | TCD_Title | component | Tester | Status | HSD | HCC/MCC | Mode | Comments
1508602363 | [Post-Si] MRC should dump the SPD for each channel or slot populated | bios.mrc_server | Hari | Pass |  | HCC | BMOD
1508602888 | [PreSiPostSi] BIOS support for fast RAPL duty cycle | bios.cpu_pm | Hari | Pass |  | HCC | BMOD
1508603007 | [Pre-Si Post-Si] Support for C1 Auto demotion undemotion | bios.cpu_pm | Hari | Fail | 16016297562 | HCC | FMOD S3M | After reading Msr-read(0xe2) getting output as 0x0 , so bit 26 and 28 getting 0 instead of 1
1508603011 | [PostSi] SpeedStep Technology | bios.cpu_pm | Hari | Pass |  | HCC | FMOD S3M
1508603137 | BIOS: Support variable serial port baud rates | bios.platform | Hari | Pass |  | HCC | BMOD
1508603165 | [Pre-Si Post-Si] Need a BIOS menu option which enables running RMT after every advanced training step for Validation data collection | bios.mrc_server | Hari | Pass |  | HCC | BMOD
1508603195 | [Post-Si Pre-Si]To validate BIOS shall support SMBUS | bios.platform | Hari | Pass |  | HCC | BMOD
1508603387 | [Pre-Si Post-Si] CHA or LLC Power Clock modulation based on CHA activity | bios.uncore | Hari | Fail | 18022014037 | HCC | BMOD | Step4, getting pythonsv command error Read transaction not succesful
1508603652 | [Post-Si] Data Scrambling for DDR is support on BIOS setup | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
1508603662 | [Pre-Si Post-Si]SMBIOS Type 17 -Memory Device | bios.platform | Chetana | Pass |  | HCC | BMOD
1508603688 | [Pre-Si]Enable or Disable or Configure Periodic Comp check | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
1508603707 | [PSS]Logging of DIMM Info check | bios.platform | Chetana | Pass |  | HCC | BMOD
1508603712 | [Pre-Si Post-Si]SMBIOS Type 1 -System Information | bios.platform | Chetana | Pass |  | HCC | BMOD
1508603759 | [Pre-Si Post-Si]SMBIOS Type 2 - Baseboard (or Module) Information | bios.platform | Chetana | Pass |  | HCC | BMOD
1508603769 | [Pre-Si Post-Si]SMBIOS Type 4 - Processor Information | bios.platform | Chetana | Pass |  | HCC | BMOD
1508603777 | [Pre-Si Post-Si]SMBIOS Type 8 - Port Connector Information | bios.platform | Chetana | Pass |  | HCC | BMOD
1508603784 | [Pre-Si Post-Si]SMBIOS Type 32 - System Boot Information | bios.platform | Chetana | Pass |  | HCC | BMOD
1508604064 | [Post-Si] Verification for PM BIOS knob LTR IIO Input | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
1508604170 | [Post-Si] CPU Flex Ratio Override | bios.cpu_pm | Chetana | Pass |  | HCC | FMOD S3M
1508604198 | [Pre-Si Post-Si] C-State residency check - C state control switch | bios.cpu_pm | Chetana | Pass |  | HCC | FMOD S3M
1508604614 | Check GBT or XML-CLI support in UEFI shell | bios.platform | Chetana | Pass |  | HCC | BMOD
1508604652 | [Pre-Si Post-Si] To validate Bios knob for directory optimization in CHA for Crystal Ridge | bios.uncore | Chetana | Pass |  | HCC | BMOD
1508604681 | Command Timing check | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
1508605002 | [Post-Si]MSR MISC_PWR_MGMT test in HWPM Native mode with No legacy support | bios.cpu_pm | Chetana | Fail | 16016818274 | HCC | FMOD S3M | Getting incorrect value while reading reading MSR(0x1AA)
1508605194 | [Pre-Si ]Enable or Disable ZQCAL check | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
1508605237 | Check GBT and XML Cli functionality | bios.platform | Chetana | Pass |  | HCC | BMOD
1508605330 | [Pre-Si & Post-Si] To verify memory power down mode options | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
1508605402 | [Pre-Si Post-Si] Verify Core Disable Option | bios.platform | Chetana | Pass |  | HCC | BMOD
1508605570 | [Pre-Si Post-Si] C-States MSR check (0XE2) | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
1508605748 | [Pre-Si Post-Si]BIOS knob to enable or disable DBP feature check | bios.uncore | Chetana | Pass |  | HCC | BMOD
1508605865 | [Post-Si Pre-Si]BIOS program XPT_32_ENTRY_PREFETCH_BASE registers to 0 for UMA based clustering | bios.uncore | Chetana | Pass |  | HCC | BMOD
1508605900 | [Post-Si Pre-Si] To check LIMCA Knob is removed from BIOS Setup Page. | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
1508605916 | To validate Bios to support SVOS operating system | bios.platform | Chetana | Pass |  | HCC | BMOD
1508606108 | [Pre-SiPost-Si] BIOS Support for Hardware P-States and Energy Perf BIAS | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
1508606168 | [Pre-Si Post-Si] Verify Bios an option to Enable_Disable Package RAPL Limit MSR Lock | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
1508606208 | Verify Bios boot time | bios.platform | Chetana | Pass |  | HCC | BMOD
1508606427 | [Post-Si]Memory FRB check during memory training phase. | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
1508606520 | [Post-Si] Check if UEFI driver NacUndi is added in BIOS image. | bios.platform | Chetana | Pass |  | HCC | BMOD
1508606640 | Verify standalone S3M FW FIT Table & unified patch(core and uncore fw) integration status via Fitgen tool | bios.platform | Chetana | Pass |  | HCC | BMOD
1508606652 | [Pre-Si Post-Si] Verify Updated EPB config register to the tuned SAPM DLL value | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
1508607234 | [Pre-Si Post-Si]SMBIOS Type 0 - BIOS Information | bios.platform | Chetana | Pass |  | HCC | BMOD
1508607296 | [Pre-Si Post-Si] To validate OSB enabled in multi-socket with directory mode enabled | bios.uncore | Chetana | Pass |  | HCC | BMOD
1508607374 | Verify Bios DRAM RAPL option to enable or Disable | bios.cpu_pm | gangani | Pass |  | HCC | FMOD S3M
1508607823 | [ Post-Si]To validate Bios Setup Knob Enable / Disable ACP is programmed. | bios.cpu_pm | gangani | Pass |  | HCC | FMOD S3M | sv.socket0.uncore.punith_multi0.ptpcioregs.ptpcioregs.capid10.show() run this cmd to get the expected values.
1508607824 | [Pre-Si Post-Si] To validate CHA Multicast on SPR GPSB Gen 2.0 | bios.uncore | gangani | Fail | 18022014037 | HCC | BMOD | error in python cmd : Read transaction not successful
1508607892 | [Pre-Si Post-Si]SMBIOS Type 7 - Cache Information | bios.platform | gangani | Pass |  | HCC | BMOD
1508608060 | BIOS can support RTC Wake from S4 or S5 | bios.platform | gangani | Pass |  | HCC | BMOD
1508608135 | [Pre-Si Post-Si]SMBIOS Type 16 - BIOS Information (Physical Memory array) | bios.platform | gangani | Pass |  | HCC | BMOD
1508608138 | [Pre-Si Post-Si] Drop SoC support for T-states | bios.cpu_pm | gangani | Pass |  | HCC | FMOD S3M
1508608187 | [Pre-Si Post-Si] Verify System Information in Bios and OS | bios.platform | gangani | Pass |  | HCC | BMOD
1508608465 | [Post-Si]MPV needs a knob that will force the CPU frequency registers to be unchanged. | bios.cpu_pm | gangani | Block |  | HCC | FMOD S3M | step: 3 error in simics console cmd actual o/p: S0C0T0 msr(0x194) = 0x0 expected o/p: non-zero value
1508608672 | [Post-Si]Fast cold boot support with Min populated DDR4 DIMM | bios.mem_decode | gangani | Pass |  | HCC | BMOD
1508608677 | [Pre-Si & Post-Si] Verify PMAX Detector Enhancement and Detector knobs behavior. | bios.cpu_pm | gangani | Pass |  | HCC | FMOD S3M
1508609113 | [Pre-Si] [Post-Si] To validate mcaonnonnemcacheablemmio default value is 1 | bios.uncore | gangani | Pass |  | HCC | BMOD
1508609355 | [Pre-Si Post-Si] To validate BIOS should set MMIOH Granularity to 64GB by default | bios.platform | gangani | Pass |  | HCC | BMOD
1508610148 | [Pre-Si] To verify BIOS can detect valid Punits | bios.uncore | gangani | Pass |  | HCC | BMOD
1508610279 | [Pre-Si Post-Si] BIOS shall enable eSPI Decode (LDE) | bios.platform | gangani | Pass |  | HCC | BMOD
1508610555 | To check I3C native mode support for DDR5 | bios.mrc_server | gangani | Block |  | HCC | BMOD | step 6: change knob I3C mode "disable" after reset and search I3C mode in log that is still present in log
1508610606 | [Post-si] To validate BIOS shall support Monitor Mwait Enable | bios.cpu_pm | gangani | Pass |  | HCC | BMOD
1508611262 | [Pre-Si Post-Si] To validate the XPT PREFETCH CONFIG1 register | bios.uncore | gangani | Pass |  | HCC | BMOD
1508613277 | Collect Performance Data from UEFI shell | bios.platform | gangani | Pass |  | HCC | BMOD
1508613485 | [Pre-Si Post-Si] Verify the number of memory controllers | bios.mem_decode | gangani | Pass |  | HCC | BMOD
1508613620 | [Pre and Post Si] Patrol Scrub Enable at End of POST | bios.ras | gangani | Pass |  | HCC | BMOD
1508615408 | [Pre-Si Post-Si]SMBIOS Type 3 - System Enclosure or Chassis | bios.platform | gangani | Pass |  | HCC | BMOD
1508615418 | [Pre-Si Post-Si] SMBIOS Type 11 - OEM Strings and Type 12 - System Configuration Options | bios.platform | gangani | Pass |  | HCC | BMOD
1508615437 | [Pre-Si Post-Si]SMBIOS Type 38 - IPMI Device Information | bios.platform | gangani | Pass |  | HCC | BMOD
1508615507 | [Pre-Si Post-Si]SMBIOS Type 13 - BIOS Language Information | bios.platform | gangani | Pass |  | HCC | BMOD
1508615521 | [Pre-Si Post-Si]SMBIOS Type 19 - Memory Array Mapped Address | bios.platform | gangani | Pass |  | HCC | BMOD
1508615533 | [Pre-Si Post-Si]SMBIOS Type 27 - Cooling Device | bios.platform | Feby | Pass |  | HCC | BMOD
1508615540 | [Pre-Si Post-Si]SMBIOS Type 9 -System Slots | bios.platform | Feby | Pass |  | HCC | BMOD | As CTC team confirmed Valueswill vary and values given in test case is example.
1508615583 | [Pre-Si Post-Si]SMBIOS Type 39 -System Power Supply | bios.platform | Feby | Pass |  | HCC | BMOD
1508615618 | [Pre-Si Post-Si] Verify BIOS implementation from EDK2 which uses only Admin password. | bios.platform | Feby | Pass |  | HCC | BMOD
1508616007 | [Post-Si] MRC should dump the SPD for each channel or slot populated | bios.mrc_server | Feby | Pass |  | HCC | BMOD
1508780448 | [Pre-Si & Post-Si] Check CHA 7-bit interleave list support | bios.mem_decode | Feby | Pass |  | HCC | BMOD
1508780617 | [Pre-Si Post-Si] check 16 general purpose DRAM decoders and 14 remote DRAM decoders support | bios.mem_decode | Feby | Pass |  | HCC | BMOD
1508780676 | [Pre-Si Post-Si] check CHA second-level decode interleave granularities | bios.mem_decode | Feby | Pass |  | HCC | BMOD
1508780727 | [Pre-Si Post-Si] check support for first-level memory decode interleave granularities of 256B, 512B, 1KB, 2KB, 4KB and 8KB | bios.mem_decode | Feby | Pass |  | HCC | BMOD
1508780778 | [Pre-Si Post-Si] check CHA 1-way interleaving target in SAD DRAM rule | bios.mem_decode | Feby | Pass |  | HCC | BMOD
1508781056 | [Pre-Si Post-Si] check CHA general-purpose route tables | bios.mem_decode | Feby | Pass |  | HCC | BMOD
1508783492 | [Pre-Si Post-Si] check CHA second-level decode interleave ways | bios.mem_decode | shariff | Pass |  | HCC | BMOD
1508783501 | [Pre-Si Post-Si] check CHA route table 6-bit target ID, 2-bit channel ID | bios.mem_decode | shariff | Pass |  | HCC | BMOD
1508783530 | [Pre-Si Post-Si] check B2CMI TAD register refactoring | bios.mem_decode | shariff | Pass |  | HCC | BMOD
1508976568 | [Pre-si][GNR/SRF] BIOS Basic Boot to Windows OS/Linux/Busybox on Simics VP | bios.platform | shariff | Pass |  | HCC | BMOD
1509009327 | [Pre-Si] DDR5 Memory Speed (2DPC) - platform capability | bios.mrc_server | shariff | Pass |  | HCC | BMOD
1509009361 | [IP][MRC] DDR Frequency (Data Rate) | bios.mrc_server | shariff | Pass |  | HCC | BMOD
1509041141 | [Post-Si] BIOS support for integrated/discrete Clock on BirchStream | bios.platform | Feby | Pass |  | HCC | BMOD
1509105312 | [Pre Si & Post Si] Verify BHS have removed the Dynamic L1 knob and settings for bit IIO_DYNAMIC_L1_DISABLE of READ/WRITE_PCU_MISC_CONFIG. | bios.cpu_pm | shariff | Pass |  | HCC | BMOD
1509185807 | [Post-Si]UEFI support BMC remote setup settings configuration. | bios.platform | shariff | Pass |  | HCC | BMOD
1509379703 | Verify DFX Setup Options to Enable/Disable XOR | bios.mem_decode | Hari | Pass |  | HCC | BMOD
1509818812 | [Pre-Si & Post-Si] Thermal Throttling enable by MRC | bios.mrc_server | shariff | Pass |  | HCC | BMOD
1509986822 | check CPUID program | bios.uncore | shariff | Pass |  | HCC | BMOD
1509987918 | Show the simics variables list | bios.platform | Feby | Pass |  | HCC | BMOD
1509991302 | Update write_err_latency register programming for Gen3 GearRate | bios.mrc_server | Feby | Pass |  | HCC | BMOD
1509998413 | Compare Setup Knobs by xmlcli tool | bios.platform | Hari | Pass |  | HCC | BMOD
14014449779 | MRC shall output warning, if a given channel is populated with MCR and any other dimm type | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010008243 | Verifying Critical Threshold values in bios to Enable IO enforced ordering | bios.uncore | shariff | Pass |  | HCC | BMOD
15010024500 | Check Memhot Out configuration AFTER TSOD polling is available | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010034853 | Review code for compliance with MC FAS cold boot sequences | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010078543 | Review code for compliance with MC FAS warm boot sequences | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010116652 | [GNRD] CAPID programming | bios.platform | shariff | Pass |  | HCC | BMOD
15010120240 | To Verify DPT enhancement in CHA | bios.uncore | Feby | Pass |  | HCC | BMOD
15010120455 | To verify Pcie devices in order of SOC Pkg Numbering | bios.uncore | shariff | Pass |  | HCC | BMOD
15010127375 | Support SMBUS instance mapping - GNR-D MCC / HCC | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010137351 | To verify the Port IDs and BARs wrt GNRD – Uncore | bios.uncore | shariff | Pass |  | HCC | BMOD
15010139402 | [GNR-D]Check RP FW Build Use case(Debug/Release) | bios.platform | Hari | Pass |  | HCC | BMOD
15010185782 | [Post-Si][Pre-Si]To Verify Enhance RSF for IODC | bios.uncore | shariff | Pass |  | HCC | BMOD | executed " sv.socket0.soc.cha_multi.sad.ha_coh_cfg.show() , sv.socket0.compute0.uncore.cha.cha0.pipe.cbo_coh_config.show() as per the attcahements - Getting expected output
15010186183 | Boot successfully with kaseyville-sp.simics | bios.platform | shariff | Pass |  | HCC | BMOD
15010191527 | To verify S3M FW mailbox handler and mailbox requester must use sync point to ensure S3M is ready to accept data stream | bios.uncore | shariff | Pass |  | HCC | BMOD
15010198579 | Check whether ipmi2.0 specification is supported | bios.platform | shariff | Pass |  | HCC | BMOD
15010215708 | Verify DRAM on platform | bios.mrc_server | Hari | Pass |  | HCC | BMOD
15010231461 | Verify register value after knob changed for Rowhammer Adaptive RFM | bios.mrc_server | shariff | Fail | 16016817849 | HCC | BMOD | After changing knob to "pTRR DDR to ENABLE" and "PTRR Victim Refresh Mode to +1/-1/+2/-2" got result with '0' values instead of non zero values
15010287572 | Validate the support of PTRR DDR knob | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010295190 | verify PMON offsets | bios.uncore | shariff | Pass |  | HCC | BMOD
15010356986 | Enable CA Scrambler feature for MCR | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010357324 | CPU self-boot without PCH | bios.uncore | shariff | Pass |  | HCC | BMOD
15010379750 | TO verify uncore initialization includes CHA, Ubox, M2IOSF, HQM, PCIe root port enumeration | bios.uncore | shariff | Pass |  | HCC | BMOD
15010379895 | To verify register capid1_19 was removed after gnrd_soc_mcc_21ww37_2 for GNRD | bios.uncore | shariff | Pass |  | HCC | BMOD
15010380160 | verify Uncore ASI file from ACPI | bios.uncore | Chetana | Pass |  | HCC | BMOD
15010380383 | Verify ASL entries of stacks removed in ACPI table | bios.platform | shariff | Pass |  | HCC | BMOD
15010396727 | To verify CHA DBP register fields drop clean evictions even if not dead | bios.uncore | shariff | Pass |  | HCC | BMOD
15010407454 | Verify CHA register tor_thresholds_cfg.prq_count_threshold | bios.uncore | gangani | Pass |  | HCC | BMOD
15010453277 | To verify SNC register related to SPK | bios.uncore | Hari | Pass |  | HCC | BMOD
15010457036 | To verify CHA register programming | bios.uncore | gangani | Pass |  | HCC | BMOD
15010490163 | BIOS should program DIMM_TYPE register for the polling control during PkgC | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010680434 | BIOS Opt-in knob for out-of-band Agent toAccess Downstream MMIO Register space | bios.uncore | Chetana | Pass |  | HCC | BMOD
15010695640 | [EGS] Warm reset during BIOS boot flow | bios.cpu_pm | shariff | Pass |  | HCC | BMOD
15010750901 | Configure MC for DDR5 or MCR mode before DDR training | bios.mrc_server | shariff | Pass |  | HCC | BMOD
15010783482 | Verify CMI Init Option is removed from setup. | bios.mrc_server | Hari | Pass |  | HCC | BMOD
15010797404 | Verify calltable PMIC supporting during MRC phase | bios.mrc_server | Hari | Pass |  | HCC | BMOD
15010833490 | capture the DDRIO trace when XoverCalibration is executing | bios.mrc_server | Hari | Pass |  | HCC | BMOD
15011101508 | Check the knob functionality for MC Disable. | bios.mrc_server | Hari | Pass |  | HCC | BMOD
16012239274 | [Pre-Si Post-Si] To Verify Bios an option to Configure Hardware P-State (Native mode, OOB ) MSR 0X1AA | bios.cpu_pm | Hari | Fail | 16016818274 | HCC | FMOD S3M | Getting incorrect value while reading reading MSR(0x1AA)
16012489977 | To verify dynamic detection of SPD files in SIMICS with BIOS (Golden scripts) | bios.platform | Hari | Pass |  | HCC | BMOD
16012511779 | To verify BIOS to program SEGIDREG0.SEGID0 as SegID for IEH | bios.ras | Hari | Pass |  | HCC | BMOD
16012577838 | To verify BIOS shall detect active B2CMI devices using CAPID3 register MC enable info on every present compute die and get the total count of enabled MC | bios.uncore | Hari | Pass |  | HCC | BMOD
16012616661 | [Pre-Si & Post-Si] To verify support for local error registers of error logger in BIOS IEH Error handler.by injecting I3C correctable error | bios.ras | Hari | Block |  | HCC | BMOD | RAS Feature Block
16012703150 | [Post-Si] To Check default data at build time and decompress them into Data Cache | bios.platform | Hari | Pass |  | HCC | BMOD
16012706362 | To validate PCU_CR_DESIRED_CORES_CFG register | bios.cpu_pm | Hari | Pass |  | HCC | FMOD S3M
16012710104 | RAS - Verify FunnyIO Map and PLA Changes for 16 Bit Port IDs | bios.ras | Feby | Pass |  | HCC | BMOD | https://hsdes.intel.com/appstore/article/#/16015592311 -register will get changed when BIOS adds/removes SB access programming.
16012801464 | Patrol scrub register verification changes | bios.ras | Hari | Pass |  | HCC | BMOD
16012832585 | [Pre-Si & Post-Si] To verify RCECABN register for wave 3 -- IEH RCEC Next bus/last bus programming | bios.ras | Feby | Pass |  | HCC | BMOD
16012967177 | IO Die Stack Configuration Check - FlexUPIy (Sx) | bios.uncore | Feby | Pass |  | HCC | BMOD
16013023908 | To validate MSR_CRASHLOG_CONTROL_REGISTER definition for EnGprs bit needed to enable GPR crashlog/Core Crash | bios.cpu_pm | Feby | Pass |  | HCC | FMOD S3M
16013072581 | To validate OOBMSM Multi-Die Support (Master /Slave) | bios.uncore | Feby | Block |  | HCC | BMOD | python command not working in FMOD config. Updating existing HSD
16013094343 | GNR MC: Hidden registers that are accessed by BIOS - mcdata | bios.ras | Feby | Pass |  | HCC | BMOD
16013100653 | To verify BIOS shall program ROOTBUS register correctly for each HIOP instance | bios.uncore | Feby | Fail | 16015592579 | HCC | BMOD | [GNRD]: ROOTBUS register values are incorrect for each HIOP instance
16013184461 | Verify BIOS implemented with change in register definitions for Memory Error injection | bios.ras | Hari | Pass |  | HCC | BMOD
16013761117 | To validate BIOS basic support when SNC is disabled | bios.uncore | Feby | Pass |  | HCC | BMOD
16013856473 | [Pre-Si & Post-Si] To verify rank status with MCR x8 Memory dimm configuration | bios.mrc_server | Feby | Pass |  | HCC | BMOD
16014302646 | To verify bios pcode mailbox register values using B2P mailbox interface | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014302756 | Verify the option CMS ENABLE DRAM PM is removed from the BIOS menu - RAPL | bios.mrc_server | Feby | Pass |  | HCC | BMOD
16014361056 | [Pre-Si & Post-Si] To verify MCR dram_x8 memory dimm configuration | bios.mrc_server | Feby | Pass |  | HCC | BMOD
16014366509 | To validate BIOS knob for opportunistic-LLC-to-SF migration feature | bios.uncore | Feby | Pass |  | HCC | BMOD
16014492421 | Verify Legacy boot option not present in BIOS page | bios.platform | Feby | Pass |  | HCC | BMOD
16014496583 | [Pre-Si & Post-Si] Lane reversal flow for MCP emulation model | bios.mrc_server | Feby | Pass |  | HCC | BMOD
16014526968 | [Pre-Si & Post-Si] Register bit of THR_CTRL0 mr4temp Throttle Mode and Throttle Enable should be set as per MC FAS by MRC | bios.mrc_server | Feby | Pass |  | HCC | BMOD
16014554388 | [Pre-Si & Post-Si] Check t_rrsg value in MC based on the frequency selected for DDR5 | bios.mrc_server | Hari | Pass |  | HCC | BMOD
16014557822 | [Pre-Si & Post-Si] Check t_rrsg value in MC based on the frequency selected for MCR DIMMs | bios.mrc_server | Hari | Pass |  | HCC | BMOD
16014566571 | [Pre-Si & Post-Si] ddrcc_train_ctl2.sample_sel is set to 0 for DCA training step by MRC | bios.mrc_server | Feby | Pass |  | HCC | BMOD
16014588156 | To validate Disable/unused DDRIO controllers and channels with X1 Config Half population | bios.mrc_server | shariff | Pass |  | HCC | BMOD
16014604975 | MBE shall be disabled on b2idi instances connected to SPK | bios.uncore | shariff | Pass |  | HCC | BMOD
16014636884 | [Pre-Si & Post-Si] bank_scheduler_selection and page_table_index_selection programming for Gen3 for MCR | bios.mrc_server | shariff | Pass |  | HCC | BMOD
16014636911 | [Pre-Si & Post-Si] bank_scheduler_selection and page_table_index_selection programming for Gen3 for DDR5 | bios.mrc_server | shariff | Pass |  | HCC | BMOD
16014658044 | Verify BIOS support MBA4.0 and Verify UBOX registers mapping | bios.uncore | shariff | Pass |  | HCC | BMOD
16014717731 | [Pre-Si & Post-Si] Verify CLTT temperature settings for TSOD by MRC as per CLTT doc | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014722237 | [Pre-Si & Post-Si] Verify x4modesel.dimm0/1_mode to 1 for x4 DRAMs | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014764882 | To verify x4modesel.dimm0_mode set to 0 for x8 MCR DIMMs and set to 1 for x4 MCR DIMMs | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014777372 | To verify IIO stack ID assignment | bios.uncore | gangani | Pass |  | HCC | BMOD
16014794198 | [Pre-Si & Post-Si] Verification of Memory Thermal BIOS Menu Options for MEMTRIP and THERMTRIP | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014795784 | Verification of Memory Thermal BIOS Menu Options for MEMHOT_IN | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014841919 | To validate Disable/unused DDRIO controllers and channels with Full Population in 2DPC | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16014853886 | [Pre-Si & Post-Si] Verification of Memory Thermal BIOS Menu Options for MEMHOT_OUT | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16015335982 | TestSignalBitMaskRMT to choose which parameters to run during RMT | bios.mrc_server | gangani | Pass |  | HCC | BMOD
16015401793 | Verify CAPID registers fileds changes for RAS domain | bios.ras | gangani | Pass |  | HCC | BMOD
16015612982 | Verify Data Scrambling status with MCR Dimms | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
16015902650 | Direct To UPI (D2C) , Direct To Core (D2K) - Functionalilty Check on GNR | bios.uncore | Chetana | Pass |  | HCC | BMOD
16016206044 | To validate BIOS is retrieving MC frequency and MC voltage in serial logs | bios.mrc_server | Chetana | Pass |  | HCC | BMOD
16016398700 | Validate Channel disabling by configuring DDR Channel Mask knob | bios.mrc_server | gangani | Pass |  | HCC | BMOD
18020730723 | Verify RTC wake from S5 through ICT tool | bios.platform | Chetana | Block |  | HCC | BMOD | ICT tool is not available
22012000707 | [PSS & Psost-Si] BIOS to validate removal of Scalability, Turbo ratio cores knob. | bios.cpu_pm | Chetana | Pass |  | HCC | BMOD
22012003525 | To validate Dielet - Total Count, Die ID, HIOP Stacks present | bios.uncore | Chetana | Pass |  | HCC | BMOD
22012132962 | [PSS & Post-Si] To validate Distributed PkgC with Voltage actions | bios.cpu_pm | Hari | Pass |  | HCC | FMOD S3M
22012239317 | [Pre-Si & Post-Si] To check PCH devices option removed from bios knob configuration | bios.platform | Hari | Pass |  | HCC | BMOD
22012249402 | Intel Turbo Boost Technology - Energy Efficient Turbo | bios.cpu_pm | Hari | Pass |  | HCC | FMOD S3M
22013723207 | [Pre-Si & Post-Si] To verify CLTT Registers Programmed for Different Memory Frequency in 2DPC configuration | bios.mrc_server | Hari | Pass |  | HCC | BMOD
1508602809 | [Pre and Post Si] [Linux] Validate PCIE CE using EINJ tool with IOMCA option enabled in BIOS | bios.ras | Feby | Fail | 16016680042 | HCC | BMOD | Hardware error not logged in OS after Pcie Error injection
1309576291 | GNRD MCC config support | bios.iio | fklos | Pass |  | HCC | BMOD
1508603490 | PCIe Speed Limiting | bios.iio | mklarkox | Pass |  | HCC | BMOD
1508603498 | PCIe ports Max Payload control | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508603929 | SRIS enabling verification IIO | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508603944 | IIO PTM Support Verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508604005 | NPK BAR programming | bios.iio | msuchorx | Fail | 18022014037 | HCC | BMOD
1508604030 | NTB Large BAR size | bios.iio | fklos | Fail | 18022142847 | HCC | BMOD
1508605583 | Dynamic Link Width verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508605595 | PCS Mux register programming | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508609913 | Hot Plug support for IIO root ports | bios.iio | msuchorx | Block | 18021346127 | HCC | BMOD
1508610880 | ACSCAP register programming | bios.iio | pcichocx | Pass |  | HCC | BMOD
1508610971 | Clock gating support for gen5 root ports | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508610990 | ENQCMD ENQCMDS programming verification | bios.iio | msuchorx | Fail | 18022058415 | HCC | BMOD
1508611015 | FlexBusLogPhy initialization verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508611558 | HQM CPM TIP devices visibility verification | bios.iio | msuchorx | Block | 18022159941, 16016319953 | HCC | BMOD
1508611616 | Extended Tag and 10-bit support verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508611629 | DSA devices initialization | bios.iio | pcichocx | Pass |  | HCC | BMOD
1508612372 | Channel select enabling for CXPSMB verification | bios.iio | msuchorx | Block | 18021346127 | HCC | BMOD
1508612390 | CXL Debug mode verification | bios.iio | pcichocx | Pass |  | HCC | BMOD
1508612465 | Equalization bypass verification | bios.iio | pcichocx | Pass |  | HCC | BMOD
1508612479 | PXM pci bus verification | bios.iio | fklos | Fail | 18020512468 | HCC | BMOD
1508612491 | VT-d DMAR Verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508612607 | VMD PCIe Stack presence verification | bios.iio | fklos | Fail | 18022197925 | HCC | BMOD
1508614168 | IOSF data parity check | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508615478 | PSMI SCRPD1 programming verification | bios.iio | msuchorx | Fail | 18022014037 | HCC | BMOD
1508615928 | Command Parity Detection and early exit from idle for HCx verifcation | bios.iio | pcichocx | Fail | 18020509880 | HCC | BMOD
1508616162 | M2IOSF credits programming verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
14014498468 | M2IOSF flags disable_vmd_rx_mailbox and disable_vmd_tx_mailbox verification | bios.iio | pkochanx | Fail | 18022197925 | HCC | BMOD
15010304123 | IBL ITSS initialization verification | bios.pch | pcichocx | Pass |  | HCC | BMOD
18014442584 | CXL 2.0 device initialization | bios.iio | msuchorx | Pass |  | HCC | BMOD
18014542624 | CXL 1.1 device initialization | bios.iio | msuchorx | Pass |  | HCC | BMOD
18014678546 | CXL1.1 type 1 link training verification. | bios.iio | msuchorx | Pass |  | HCC | BMOD
18014678990 | CXL1.1 type 2 link training verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18014679073 | CXL1.1 type 3 link training verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18014844349 | Devices hiding verification | bios.pch | msuchorx | Pass |  | HCC | BMOD
18014846127 | IBL SMBUS initialization verification | bios.pch | pcichocx | Pass |  | HCC | BMOD
18015428175 | CXL swizzling | bios.iio | msuchorx | Pass |  | HCC | BMOD
18015436622 | CXL bifurcation support | bios.iio | msuchorx | Fail | 18022146946 | HCC | BMOD
18015581688 | CXL1.1 x4 and x8 bifurcation support verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18016008164 | ACSCTL register value verification | bios.iio | mklarkox | Pass |  | HCC | BMOD
18016902174 | Downstream port preset for Gen3 Gen4 Gen5 verification | bios.iio | pcichocx | Pass |  | HCC | BMOD
18016910418 | VMD lock bit programming | bios.iio | mtrylewx | Pass |  | HCC | BMOD
18017284388 | CXL1.1 Extended and 10-b tag support verification | bios.iio | pcichocx | Pass |  | HCC | BMOD
18017293340 | CXL1.1 ASPM verification | bios.iio | pcichocx | Pass |  | HCC | BMOD
18017293658 | CXL1.1 Max Payload Size support | bios.iio | pcichocx | Pass |  | HCC | BMOD
18017293726 | CXL1.1 MRRS support | bios.iio | pcichocx | Pass |  | HCC | BMOD
18017412257 | NAC devices enumeration verification | bios.iio | fklos | Fail | 18022237744 | HCC | BMOD
18017670778 | LVF card training verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18017760568 | SRIS in NTB mode verification | bios.iio | fklos | Fail | 18022142847 | HCC | BMOD
18017906762 | Snoop timer values verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18017963346 | Force PCI MMIOL resource allocation rebalance | bios.iio | mklarkox | Fail | 18022197925 | HCC | BMOD
18017968690 | Force PCI MMIOH resource allocation rebalance | bios.iio | mklarkox | Fail | 18022142847 | HCC | BMOD
18018018062 | LVF2 card training verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18018079443 | Enable all PCI ports | bios.iio | msuchorx | Pass |  | HCC | BMOD
18018319276 | Enable/Disable CPU Trace Hub for AET event tracing | bios.iio | mklarkox | Pass |  | HCC | BMOD
18018337578 | Hot Plug support for CXL2.0 root ports | bios.iio | msuchorx | Block | 18021346127 | HCC | BMOD
18018363071 | Native PCIe Enclosure Management support | bios.iio | fklos | Fail | 18020968519 | HCC | BMOD
18018447197 | CXL 2.0 BAR programming verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18018447269 | CXL 1.1 BAR programming verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18018472644 | Enable CXL knobs in IIO menu | bios.iio | msuchorx | Fail | 18022146946 | HCC | BMOD
18018644610 | MCTP enablement over all IIO ports | bios.iio | msuchorx | Pass |  | HCC | BMOD
18018661403 | CXL1.1 cards connected to all available PCIe stacks with enabled VT-d | bios.iio | pcichocx | Pass |  | HCC | BMOD
18018737116 | CXL2.0 devices connected to single IIO stack | bios.iio | msuchorx | Fail | 18022146946 | HCC | BMOD
18018781755 | Enqueue Capability for PCIe check | bios.iio | fklos | Pass |  | HCC | BMOD
18019251844 | SierraPeak memory allocation (SCF BAR space) | bios.iio | msuchorx | Pass |  | HCC | BMOD
18019346249 | BANK14 registers programming | bios.iio | fklos | Pass |  | HCC | BMOD
18019377034 | VMD registers programming GNR/SRF | bios.iio | msuchorx | Pass |  | HCC | BMOD
18019386689 | HIOP bank decoder programming for IIO stack GNR | bios.iio | mklarkox | Pass |  | HCC | BMOD
18019386844 | HIOP bank decoder programming for DINO stack GNR | bios.iio | mklarkox | Pass |  | HCC | BMOD
18019412822 | GNR-D IRDT table generation with CXL1.1 | bios.iio | fklos | Pass |  | HCC | BMOD
18019483594 | NVME training verification (4xNVME on stack) | bios.iio | msuchorx | Pass |  | HCC | BMOD
18019598553 | CXL Header Bypass | bios.iio | pcichocx | Pass |  | HCC | BMOD
18019672169 | IIO PCIe Compliance Mode | bios.iio | fklos | Pass |  | HCC | BMOD
18019672193 | Switching CXL.mem and CXL.cache capability | bios.iio | fklos | Pass |  | HCC | BMOD
18019888322 | PCIe ASPM verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18020097804 | vGPIO initialization verification | bios.pch | pcichocx | Pass |  | HCC | BMOD
18020194305 | IIO error checklist | bios.iio | fklos | Block | 22011881941 | HCC | BMOD
18020233623 | ACPI GPIO Initialization Verification | bios.pch | pcichocx | Fail | 18022218662 | HCC | BMOD
18020233741 | IBL UART service initialization | bios.pch | fklos | Pass |  | HCC | BMOD
18020235609 | Host warm reset using CF9 register | bios.pch | fklos | Pass |  | HCC | BMOD
18020235622 | Host cold reset using CF9 register | bios.pch | fklos | Pass |  | HCC | BMOD
18020320235 | State after G3 verification (S5 state) | bios.pch | fklos | Pass |  | HCC | BMOD
18020391143 | 'IOAPIC 24-119 Entries' BIOS Knob verification | bios.pch | fklos | Pass |  | HCC | BMOD
18020437963 | Support CXL IDE for CXL.MEM verification | bios.iio | fklos | Pass |  | HCC | BMOD
18020497750 | 'Flash Protection Range Registers (FPRR)' BIOS Knob verification | bios.pch | fklos | Pass |  | HCC | BMOD
18020724582 | XPTDEF register programming verification | bios.iio | pcichocx | Pass |  | HCC | BMOD
18020821391 | 'After Type 8 Global Reset' BIOS Knob verification | bios.pch | msuchorx | Block | 16015341602 | HCC | BMOD
18020911129 | PCI port numeration | bios.iio | msuchorx | Pass |  | HCC | BMOD
18020928624 | GNR ECRC verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18020999795 | PIPECTL2 register programming | bios.iio | msuchorx | Pass |  | HCC | BMOD
18021007247 | HIOP dynamic OOBMSM BAR size | bios.iio | mklarkox | Pass |  | HCC | BMOD
18021017581 | CXL memory isolation support | bios.iio | mklarkox | Pass |  | HCC | BMOD
18021119052 | ACPI DSDT vs PCI check | bios.iio | mklarkox | Fail | 18021555406 | HCC | BMOD
18021147741 | NPK memory allocation verification (SNC) | bios.iio | mklarkox | Fail | 18022014037 | HCC | BMOD
18021147799 | NPK BAR programming (SNC) | bios.iio | mklarkox | Fail | 18022014037 | HCC | BMOD
18021147802 | SierraPeak memory allocation (SCF BAR space) (SNC) | bios.iio | mklarkox | Pass |  | HCC | BMOD
18021147806 | Enable/Disable CPU Trace Hub for AET event tracing (SNC) | bios.iio | mklarkox | Pass |  | HCC | BMOD
18021181463 | No resources conflict detected in Linux | bios.iio | msuchorx | Fail | 15011175298 | HCC | BMOD
18021224181 | HIOP bank decoder programming for TIP stack | bios.iio | fklos | Pass |  | HCC | BMOD
18021225124 | Turbo IP (TIP) accelerator device initialization | bios.iio | fklos | Pass |  | HCC | BMOD
18021241759 | HIOP bank decoder programming for NAC stack | bios.iio | mklarkox | Pass |  | HCC | BMOD
18021243112 | Slot number unique verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
18021398422 | DevTLB invalidation timeout | bios.iio | mklarkox | Pass |  | HCC | BMOD
18021419182 | Enable NOP check | bios.iio | msuchorx | Fail | 18022222292 | HCC | BMOD
18021734933 | Sending B2P IO_CONFIG command | bios.iio | msuchorx | Block | 14016386029 | HCC | BMOD
18021750355 | SPI and eSPI initialization verification - IBL | bios.pch | mklarkox | Pass |  | HCC | BMOD
22011878268 | PCH information presence during system boot | bios.pch | msuchorx | Pass |  | HCC | BMOD
22011878319 | HPET Timer initialization verification | bios.pch | fklos | Pass |  | HCC | BMOD
22011878324 | Dirty Warm Reset Enablement | bios.pch | fklos | Pass |  | HCC | BMOD
22011878327 | State after G3 verification (S0 state) | bios.pch | fklos | Pass |  | HCC | BMOD
22011878426 | Check SPD write disable | bios.pch | fklos | Pass |  | HCC | BMOD
22011878933 | NPK memory allocation verification | bios.iio | msuchorx | Fail | 18022014037 | HCC | BMOD
22011879055 | LTSSMSMSTS register programming verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
22011879104 | ADR options | bios.pch | fklos | Pass |  | HCC | BMOD
22011879361 | No ME BIOS code on IBL | bios.me | msuchorx | Pass |  | HCC | BMOD
22011879368 | CXL link encryption verification | bios.iio | fklos | Pass |  | HCC | BMOD
22011879384 | MADT table verification | bios.iio | pkochanx | Pass |  | HCC | BMOD
22011879387 | P2SB initialization verification | bios.pch | fklos | Pass |  | HCC | BMOD
22011879390 | ACPI PM Service initialization verification | bios.pch | fklos | Pass |  | HCC | BMOD
22011879396 | OOB bus ownership verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
22011879397 | DPC trigger and RP PIO status verification | bios.iio | msuchorx | Pass |  | HCC | BMOD
22011879402 | Bios Lock Enable feature verification | bios.pch | fklos | Pass |  | HCC | BMOD
22011897477 | Bifurcation Verification for GNR | bios.iio | msuchorx | Pass |  | HCC | BMOD
1508603501 | [TPM][PSS Post-Si]TPM2.0 Configuration and settings | bios.security |  | Pass |  | HCC | BMOD
1508605114 | [SGX][Boot Scenario Test]SGX Boot Scenario First Platform Binding | bios.security |  | Fail | New:15011234972 | HCC | BMOD
1508605439 | [TPM][PSS Post-Si]Verify TPM 2.0 Physical Presence | bios.security |  | Pass |  | HCC | BMOD
1508605466 | [MKTME][PreSi PostSi]Check whether UEFI FW generate new key or restore previous Key in NVDIMM present or S5 or cold or warm reset. | bios.security |  | Fail | 16015956171 | HCC | BMOD
1508605538 | [TPM][PSS Post-Si] dTPM_PlatformPolicyConfig_before_PlatformAuth | bios.security |  | Pass |  | HCC | BMOD
1508606061 | [MKTME][Pre-Si PostS-i]No MKTME Error Code should be displayed in the BIOS Logs for boot without MKTME BIOS flow error cases. | bios.security |  | Pass |  | HCC | BMOD
1508606066 | [MKTME][PostSi PreSi]To validate Bios write 0 to CORE_MKTME_ACTIVATION to trigger ucode | bios.security |  | Pass |  | HCC | BMOD
1508606250 | [MKTME][PreSi PostSi] Verify keyid bits | bios.security |  | Pass |  | HCC | BMOD
1508606332 | [MKTME][PreSi PostSi] To Check if MKTME is able to exclude addresses and CR Persistent memory from memory encryption. | bios.security |  | Pass |  | HCC | BMOD
1508607311 | [TPM][Pre-Si Post-Si] To validate TPM2_HierarchyChangeAuth command on every boot. | bios.security |  | Pass |  | HCC | BMOD
1508608045 | [MKTME] [PreSi PostSi][Security]Detect EFI_MEMORY_CPU_CRYPTO can encrypt memory when MKTME enabled. | bios.security |  | Pass |  | HCC | BMOD
1508608855 | [MKTME] [PreSi PostSi] [Security]TME or MKTME Support | bios.security |  | Pass |  | HCC | BMOD
1508611465 | [TPM][PSS Post-Si] TPM Replay Test | bios.security |  | Pass |  | HCC | BMOD
1508611655 | [TDX][Pre-Si Post-Si]Verify SEAMRR BASE and SEAMRR MASK is programmed correctly after TDX enable | bios.security |  | Block | 15011234972 | HCC | BMOD
1508611671 | [TDX][PostSi]Verify SEAMLDR_SVN field in MSR BIOS_SE_SVN is updated when TDX and SGX are both enabled | bios.security |  | Block | 15011234972 | HCC | BMOD
1508611684 | [TDX][PreSi PostSi]Verify the keysplit is programmed correctly during TDX initialization | bios.security |  | Block | 15011234972 | HCC | BMOD
1508611710 | [TDX][Pre-Si Post-Si]verify TDX can be enabled and disabled on BIOS setup menu | bios.security |  | Block | 15011234972 | HCC | BMOD
1508611804 | [MKTME] [PostSi PreSi]Check (MK)TME set up option when system support (MK)TME capability or not. | bios.security |  | Pass |  | HCC | BMOD
1508613530 | [SGX][Boot Scenario Test]SGX Boot Scenario Normal Boot | bios.security |  | Block | New:15011234972 | HCC | BMOD
1508613937 | [SGX][MISC Test]PRMRR register check in UEFI Shell | bios.security |  | Block | New:15011234972 | HCC | BMOD
1508614164 | [SGX][MISC Test]Verify SGX QoS setup option | bios.security |  | Block | New:15011234972 | HCC | BMOD
1508615126 | [MKTME][PSS Post-Si] Enable MKTME with Integrity | bios.security |  | Pass |  | HCC | BMOD
1508615361 | [SGX][MISC Test]BIOS will set SGX_RAS_MSR (0A3h) to opt-in SGX when SGX enabled | bios.security |  | Block | New:15011234972 | HCC | BMOD
1508615672 | [SECURE TOOL][Pre-si Post-si] Check FitGen tool to support type 4 and type 5 unified patch | bios.security |  | Pass |  | HCC | BMOD
1508916350 | [MKTME][PreSi PostSi] [Security] Verify 256bit Memory Encryption Engine (with or without integrity) | bios.security |  | Pass |  | HCC | BMOD
1508939880 | [SECURE TOOL][Pre-si & Post-si] Check FitGen tool to support S3M SOC IP | bios.security |  | Pass |  | HCC | BMOD
1509046717 | [MKTME][PreSi PostSi] [Security] Verify TME bypass mode for TME/TME-MT | bios.security |  | Pass |  | HCC | BMOD
1509113566 | [TPM] Verify TPM PCR[1] Change When Change Boot Order | bios.security |  | Pass |  | HCC | BMOD
1509425455 | [TPM] Verify TPM PCR7 Value Change After Enable Secure Boot | bios.security |  | Pass |  | HCC | BMOD
1509646275 | [MKTME][PSS Post-Si] BIOS shall restore TME_KEY during Fast Warm Reset | bios.security |  | Fail | 16015956171 | HCC | BMOD
1509916623 | [TPM] Read TPM_INTF and Check Locality0 | bios.security |  | Pass |  | HCC | BMOD
1509935854 | [TPM] TPM PCR value check - PCR0 and PCR1 | bios.security |  | Pass |  | HCC | BMOD
15010281820 | [SGX][MISC Test][GNR]SGX shall use SHA384 for RegistrationConfiguration Variable | bios.security |  | Block | New:15011234972 | HCC | BMOD
15011131624 | [TXT]Verifying ACM FW Version in BIOS Setup menu | bios.security |  | Pass |  | HCC | BMOD
16012239231 | [BOOT GUARD] Verify system behavior when Boot Guard Profile is set to 0 | bios.security |  | Fail | 15010701992 | HCC | BMOD
16012239233 | [BOOT GUARD]Verify system behavior when Boot Guard Profile is set to 5 | bios.security |  | Fail | 15010700960 | HCC | BMOD
22011877851 | [TXT]dTPM_TXT_Trust Boot_measured launch_in_RHEL | bios.security |  | Block | 15010701992 | HCC | BMOD
22011893994 | [TXT]Verify Setup option for BIOS ACM Error Reset | bios.security |  | Pass |  | HCC | BMOD
22011894096 | [TXT]dTPM_TXT_dTPM_TXTINFO | bios.security |  | Block | 15010701992 | HCC | BMOD
22011894098 | [TXT]dTPM_TXT_dTPM_GETSEC | bios.security |  | Fail | 15010701992 | HCC | BMOD
22011895042 | [TDX][Pre-Si & Post-Si]Verify M2M SEAMRR BASE and SEAMRR MASK copies are programmed correctly after TDX enable | bios.security |  | Block | 15011234972 | HCC | BMOD
22011895168 | [DMA Protection]Test DMA Protection and IOMMU programming function | bios.security |  | Pass |  | HCC | BMOD
22011895404 | [TDX][PreSi & PostSi]Verify SMRR1 and SMRR2 are Locked when TDX is enabled | bios.security |  | Block | 15011234972 | HCC | BMOD
22011895463 | [MKTME][PSS Post-Si] Enable MKTME with Integrity disabled | bios.security |  | Pass |  | HCC | BMOD
22011895794 | [TXT]Verifying ACM FW Version in BIOS Setup menu | bios.security |  | Pass |  | HCC | BMOD

## Summary
Status | Count
Pass | 292
Fail | 37
Block | 25
total | 354
Status | Percentage
Pass | 82.4859
Fail | 10.452
Block | 7.0621