## GNRD_Orange_8_D97
TCD_ID | TCD_Title | component_affected | Tester | Status | HSD | Cores | HCC\MCC | Mode | IFWI Used | Comments
1508602355 | Warm Reset - Windows | bios.cpu_pm | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508602397 | To verify Hyper-Threading(Enable LP) knob functionality when disabled | bios.cpu_pm,bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508602432 | To validate Warm Reset in EFI Shell | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508602637 | [Pre-Si Post-Si]SpeedStep (P-States) from Windows. | bios.cpu_pm | gangani | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508602684 | Verify CPUInfo in OS | bios.platform | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508602809 | [Pre and Post Si] [Linux] Validate PCIE CE using EINJ tool with IOMCA option enabled in BIOS | bios.ras | Gayathri | Block | 16015631966 | 42 | HCC | FMOD | Release IP Clean | RAS featute block
1508602932 | Support ASPEED BMC in RP UEFI | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508602991 | To verify bios F9 reset to default works | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603005 | To verify bios F10 option save works | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603037 | Verify IFWI ID and UEFI Version | bios.platform | Gayathri | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508603163 | BIOSID_005 - Validate Board name is displayed correctly in BIOS setup | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603318 | [Pre-Si Post Si]To validate system Setup Menu - Main Page | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603398 | [Pre-Si Post-Si] UEFI shell feature commands | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603400 | To Verify shutdown from UEFI shell | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603410 | Verify shutdown from OS | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603458 | [Pre-SI Post-Si]Verify warm reset through ctrl+alt+del | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603543 | [Pre-Si Post-Si] Verify reset from OS | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603774 | Keyboard and mouse function check under OS | bios.platform,bios.uncore | gangani | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508603938 | [PSS PostSi] - BIOS version visible by OS | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508603996 | To validate Cold Reset-EFI Shell | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508604005 | NPK BAR programming | bios.iio | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508605022 | [PSSPostSi] Booting the BIOS UEFI prompt | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508605199 | [Pre-Si Post-Si] To validate UPI Dfx Configuraion Knobs check | bios.uncore | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508605361 | [Post-Si] To verify BIOS Setup option control speed for DDR dimm | bios.mrc_server | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508605380 | MRC knobs created for emulation shall get ported successfully and should be functional | bios.platform | Gayathri | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508605609 | Verify CPU ID in CPU Info BIOS page | bios.cpu_pm | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508605646 | To validate POST Codes sent to PORT 80h | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508605799 | [Pre-Si Post-Si] To validate MMIO should be enable on M2IOSF | bios.uncore | Chetana | Pass |  | 42 | HCC | FMOD | Debug IP Clean
1508605916 | To validate Bios to support SVOS operating system | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508605931 | [Pre-Si Post-Si] To validate BIOS can support to enable or disable VT-D | bios.iio | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508606165 | Verification of USB connectivity feature in the SUT | bios.iio,bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508606172 | [PostSi]To check boot time to EFI and MRC training messages when both AttemptFastColdBoot_Enable AttemptFastBoot_Enable. | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508606208 | Verify Bios boot time | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508606240 | [MKTME][Pre-Si Post-Si] Validate number of keyid bits used for MKTME | bios.security | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508606364 | [Pre-Si Post-Si] To verify DDR Memory Min Population | bios.mem_decode | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508606367 | [Pre-Si & Post-Si]To validate IP Clean build boot to OS | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508606397 | To verify Hyper-Threading(Enable LP) knob functionality when enabled | bios.cpu_pm,bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508607234 | SMBIOS Type 0 - BIOS Information | bios.platform | gangani | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508607605 | Check the Presence of Release Notes | bios.platform | Gayathri | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508608365 | [PostSi][CPX6][OS] Cold Reset from UEFI Shell - 10 Cycles | bios.platform | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508608415 | [PostSi][CPX6][OS] Warm Reset from UEFI Shell - 10 Cycles | bios.platform | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508608940 | Verify Bios boot time ( Second time boot less than 30 Sec) | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508609176 | To check fast boot support with Min populated dimm | bios.mrc_server | Arpitha | Pass |  | 42 | HCC | FMOD | Debug IP Clean
1508609419 | [Pre-Si Post-Si] Serial output should print SAD and TAD CSR info. | bios.mem_decode | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508609663 | [FSP] Verify FSP dispatch build binary can boot successfully | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508609913 | Hot Plug support for IIO root ports | bios.iio | Chetana | Pass |  | 42 | HCC | FMOD | Debug IP Clean
1508610481 | [TPM][PostSi PreSi][Security] dTPM_001_Enable dTPM | bios.platform,bios.security | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508610971 | Clock gating support for gen5 root ports | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613272 | Orange - RES_003 - First time boot | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613279 | To Validate Boot to Windows | bios.platform | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508613284 | Verify Idle state in EFI and OS | bios.cpu_pm | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613290 | Verify Turbo Register | bios.cpu_pm | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613312 | Serial logs captured using serial console | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613329 | Validate CPU values are reported correclty in BIOS Setup | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613347 | Validate Board name is displayed correctly in BIOS setup | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508613374 | Validate Storage Boot check to OS(NVMe Drive) and UEFI | bios.platform | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508613686 | [SGX][MISC Test] Verify the MKTMEi with MSR IA32_TME_CAPABILITY | bios.security | gangani | Block | 15012108594 | 42 | HCC | FMOD | Release IP Clean | SGX feature Block
1508613698 | VMD driver unload test and VROC version check | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508615757 | [Post-Si Pre-Si] Generate BDBA report | bios.platform | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508615765 | [OTA][POST-SI][PSS] OTA in band support for MK-TME feature enable, disable and discovery. | bios.security | Gayathri | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508616312 | [SGX][MISC Test]Verify SGX if is enabled correctly | bios.security | gangani | Block | 15012108594 | 42 | HCC | FMOD | Release IP Clean | SGX feature Block
1508888162 | PMWA_006 - Intel SpeedStep Technology - Register | bios.cpu_pm | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
1508891715 | Orange - Boot_005.1 - Boot to Linux CentOS8.2 | bios.platform,fw.ifwi.bios | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508916350 | [MKTME][PreSi PostSi] [Security] Verify 256bit Memory Encryption Engine (with or without integrity) | bios.security | gangani | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508964015 | To check boot order sequence with bios priority | bios.platform | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
1508992924 | [SGX][MISC Test][GNR/SRF A0]SBFT should co-exit with SGX and PRMRR size should change with SBFT enable | bios.ifs,bios.security | gangani | Block | 15012108594 | 42 | HCC | FMOD | Release IP Clean | SGX feature Block
1509347883 | Verify PCIe Gen 5 enumeration, speed and width from UEFI shell and OS | bios.iio | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
13010322930 | Basic CXL2.0 enumeration test (Windows) | bios.iio | Chetana | Block |  | 42 | HCC | BMOD | Release IP Clean | Debug is in Progress
14014972315 | [Pre and Post-Si] Validate global reset function from EDK shell | bios.platform | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
15012179548 | [SGX][MISC Test][GNR B0]8M is required in PRMRR0 for SAF/SBFT | bios.ifs,bios.security | gangani | Block | 15012108594 | 42 | HCC | FMOD | Release IP Clean | SGX feature Block
16012361932 | [IC&X1&UCC] UBIOS.obj boot test on Simics | bios.platform | Gayathri | Pass |  | 42 | HCC | BMOD | Release IP Clean
16012518713 | [IC&X1&UCC] UBIOS.obj test with Full Memory population | bios.mrc_server | Gayathri | Pass |  | 42 | HCC | BMOD | Release IP Clean
16012914559 | [IC&X1&UCC]UBIOS.obj boot test with 2LM Emulation Bios knobs Modified | bios.platform | Gayathri | Pass |  | 42 | HCC | BMOD | Release IP Clean
16012916976 | [IC&X1] UBIOS.obj boot test with 4Die Gen5 Emulation Bios knobs Modified | bios.platform | Gayathri | Pass |  | 42 | HCC | FMOD | Release IP Clean
16013360414 | [Pre-Si & Post-Si] MCR Memory Full Population | bios.mrc_server | Gayathri | Block | 15011484236 | 42 | HCC | FMOD | Release IP Clean | Full Memory population feature block
16013360664 | [Pre-Si & Post-Si] To validate DDR Memory Full Population | bios.mrc_server | Gayathri | Block | 15011484236 | 42 | HCC | FMOD | Release IP Clean | Full Memory population feature block
16013360713 | [Pre-Si & Post-Si] [UCC] DDR Memory Half Population | bios.mrc_server | Chetana | Pass |  | 42 | HCC | BMOD | Release IP Clean
16013868803 | Boot Flow Check in UART print | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
16013870138 | [Pre-Si & Post-Si] Check for certain expected keywords in BIOS | bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
16014428644 | To verify booting to UEFI Shell and OS with different IIO Stack combinations | bios.iio,bios.uncore | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
16014703824 | [Pre and Post Si] [Linux] Validate Memory CE using EINJ tool with EMCA option enabled in BIOS | bios.ras | Gayathri | Block | 16015631966 | 42 | HCC | FMOD | Release IP Clean | RAS featute block
16014733091 | [Pre-Si] Validate MSR traces of MKTME with UBIOS enabled | bios.platform,bios.security | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
16014862615 | [Pre and Post Si] [Linux] Validate Memory UCE non fatal error using EINJ tool with EMCA option enabled in BIOS | bios.ras | Gayathri | Block | 16015631966 | 42 | HCC | FMOD | Release IP Clean | RAS featute block
16015036036 | To verify the value of UPI_XTOR_SOCKET_BITMAP in UBIOS_GENERATED.asm and UBIOS_GENERATED_XTOR.asm | bios.platform | Gayathri | Pass |  | 42 | HCC | BMOD | Release IP Clean
16018535968 | Verify Warm Reset and Cold Reset Power Cycle from EFI shell through CF9 Register write | bios.cpu_pm | Arpitha | Pass |  | 42 | HCC | FMOD | Debug IP Clean
16018844279 | Verify SPI BAR read and write | bios.platform | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
18014442584 | CXL 2.0 device initialization | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18014542624 | CXL 1.1 device initialization | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18014678990 | CXL1.1 type 2 link training verification | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18017412257 | NAC devices enumeration verification | bios.iio | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
18017670778 | LVF card training verification | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18018018062 | LVF2 card training verification | bios.iio | sajjad | Pass |  | 42 | HCC | FMOD | Debug IP Clean
18018198275 | OOBMSM as MCTP Bus Owner | bios.iio,bios.uncore | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18018337578 | Hot Plug support for CXL2.0 root ports | bios.iio | gangani | Block | 16015321565 | 42 | HCC | FMOD | Release IP Clean | CXL feature Block
18018447197 | CXL 2.0 BAR programming verification | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18018447269 | CXL 1.1 BAR programming verification | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18019251844 | SierraPeak memory allocation (SCF BAR space) | bios.iio | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
18019377034 | VMD registers programming GNR/SRF | bios.iio | gangani | Pass |  | 42 | HCC | FMOD | Release IP Clean
18019483594 | NVME training verification (4xNVME on stack) | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18020194305 | IIO error checklist | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
18020730053 | Verify system boot to Esxi OS | bios.platform | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
18020841864 | Verify Boot Menu list and respective action(F7) | bios.platform | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean
18022238998 | Basic PCI device training test | bios.iio | Chetana | Pass |  | 42 | HCC | FMOD | Release IP Clean
22011878933 | NPK memory allocation verification | bios.iio | gangani | Pass |  | 42 | HCC | FMOD | Release IP Clean
22011879371 | System Information Verification | bios.pch,bios.platform | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
22011879396 | OOB bus ownership verification | bios.iio | Automation | Pass |  | 42 | HCC | BMOD | Release IP Clean
22011897477 | Bifurcation Verification for GNR | bios.iio | Arpitha | Pass |  | 42 | HCC | FMOD | Release IP Clean

## Summary
Status | Count
Pass | 96
fail | 0
Block | 11
Total | 107
Status | Percentage
Pass | 89.7196
Fail | 0
Block | 10.2804