## sheet1
TCD_ID | TCD_Title | Status
14013176141 | ACPI entry for GPIO controller | PASSED | io_general.lsio_gpio | bios.pch | bios.pch,bios.platform | 14014361834,18025337918,18025343764,22012107698,22012113251,22012113286,22012116685,22012134562 | Y | PASSED | mrajan2x
16017015053 | Allocate DMI3BAR and DMI3 decode register Initialization in IOC | BLOCKED | reset | bios.platform | bios.platform | 22012121012 | Y | BLOCKED | mrajan2x | other; sent mail to CO. Awaiting for Domain Owner
14013160249 | BIOS Hotkey combination (CTRL-ALT-F1) should display by the BIOS during boot process | PASSED | manageability | bios.me | bios.me | 22012114027 | Y | PASSED | bajanthx
14013186967 | BIOS Hotkey combination (CTRL-ALT-F1) should display by the BIOS during boot process | FAILED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113958,22012113996,22012114104,22012114130 | Y | FAILED | usavithx
14013178260 | Boot to OS from M.2 NVMe-SSD connected to Add-on-card connected over PCIe-X4 Slot | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | aiyyapax
14013174056 | Check DMI is enabled by default in BIOS for Halo/ DT boards | PASSED | system | bios.sa | bios.platform,bios.sa | 22012111970,22012114256 | Y | PASSED | jmanigax
14013185270 | DPTF devices enumeration pre and post S0i3(Modern Standby) cycle | PASSED | thermal_management | bios.platform | bios.platform,fw.ifwi.tools | 22014341926 | Y | PASSED | bajanthx
14013176928 | Debug NPK after did ack | PASSED | debug | bios.platform | bios.platform | 22012112278,22012118373 | Y | PASSED | mrajan2x
14013160109 | ME FW response and version check in EFI Shell | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme |  | Y | PASSED | sksharax
14013186924 | S0/M0 transition during CS state | PASSED | manageability | fw.ifwi.csme | bios.cpu_pm,bios.me,fw.ifwi.ish | 22012113706,22012113845 | Y | PASSED | deivasix
14013187018 | S0/M0 transition during Hbernate(S4) state' | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113706,22012113845 | Y | PASSED | deivasix
14013187024 | S0/M0 transition during Hybrid sleep state | FAILED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113706,22012113845 | Y | FAILED | deivasix
14013187020 | S0/M0 transition during sleep(S3) state | FAILED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113706,22012113845 | Y | FAILED | deivasix
14013182515 | SSD Storage detection in BIOS in AHCI mode enabled | PASSED | storage | bios.pch | bios.pch | 22012133989 | Y | PASSED | jmanigax
14013160087 | Validate BIOS passes all PEP Constraints for DMS | PASSED | power_management.modern_standby | bios.cpu_pm | bios.cpu_pm,bios.platform | 22012110348,22012112731 | Y | PASSED | mrajan2x
14013163162 | Validate GOP-VBT Merge tool functionality by comparing VBT dump file from EDK shell with modified VBT file | BLOCKED | reset | bios.sa | bios.sa | 16016327645,16017517024,16019112439,22012110550,22012110930,22012118119,22012118227,22012118508,22014797382 | Y | BLOCKED | usavithx | other; CLID- 10561
14013165524 | Validate GOP-VBT Merge tool functionality with Release and Debug image | BLOCKED | reset | bios.sa | bios.sa | 22012110930 | Y | BLOCKED | usavithx | other; CLID- 10561
14013158717 | Validate PEP constraints and Hardware low power residency is achieved using sleepstudy command | PASSED | power_management.modern_standby | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | mrajan2x
16013240691 | Validate RTD3 support for Intel Gaussian Neural-Network Accelerator (GNA) with idle and CMS states in OS | BLOCKED | power_management | bios.sa | bios.sa |  | Y | BLOCKED | usavithx | other;
14013184750 | Validate System Entry/Exit Low power Audio | BLOCKED | power_management | bios.cpu_pm | bios.platform |  | Y | BLOCKED | usavithx | other; CLID-9418
14013158673 | Validate Type-C USB3 Host Mode (Type-C to A) functionality after Deep S4, Cable connected at Deep S4 State | FAILED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 22012111472,22012112748,22012112808,22012112860,22012118923,22012134022 | Y | FAILED | deivasix
14013185758 | Validate Type-C USB3.1 gen1 Host Mode functionality on hot insert and removal over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 1508914416,18025116166,22012111401,22012111472,22012112708,22012112808,22012112860,22012113799,22012118923,22012120025,22012120027,22012134022 | Y | PASSED | mrajan2x
14013172915 | Validate Type-C USB3.2 gen1 Host Mode functionality - after G3 and Warm reboot cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 18025116166,22012111472,22012112808,22012112860,22012134022 | Y | PASSED | deivasix
14013158803 | Validate Type-C USB3.2 gen2x1 host mode functionality on hot insert and removal over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 1508914416,22012112200,22012112708,22012113799,22012115176,22012115725,22012118923,22012120035 | Y | PASSED | mrajan2x
14013183790 | Validate USB 2 device enumeration when hot plug device pre and post S3 cycle over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch | 22012112722 | Y | PASSED | bajanthx
14013185476 | Validate USB 2 device hot-plug functionality over USB2 Type-A port | PASSED | audio | bios.platform | bios.pch,fw.ifwi.bios,fw.ifwi.pmc | 1509172672 | Y | PASSED | deivasix
14013185376 | Validate USB 2 devices functionality over USB Type-A port with pre and post Disconnected-MOS cycle | PASSED | io_usb | bios.pch | bios.pch,fw.ifwi.pchc |  | Y | PASSED | bajanthx
14013183898 | Validate USB 2 devices functionality over USB Type-A port with pre and post S3 cycle | PASSED | io_usb | bios.pch | bios.pch | 22012112708,22012112722 | Y | PASSED | bajanthx
14013185370 | Validate USB 3 device enumeration when hot plug device pre and post Disconnected-MOS cycle over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch,fw.ifwi.pchc,fw.ifwi.pmc |  | Y | PASSED | bajanthx
14013185378 | Validate USB 3 devices functionality over USB Type-A port with pre and post Disconnected-MOS cycle | PASSED | io_usb | bios.pch | bios.pch,fw.ifwi.pchc |  | Y | PASSED | bajanthx
14013185830 | Validate USB 3 devices functionality over USB Type-A port with pre and post S5 cycle | PASSED | io_usb | bios.pch | bios.pch,fw.ifwi.pchc | 22012112200,22012112708,22012112748 | Y | PASSED | bajanthx
14013182806 | Validate USB Mouse enumeration and functionality over USB Type-A port after S3/S0i3 cycle | PASSED | io_usb | bios.pch | bios.pch | 22012112687 | Y | PASSED | bajanthx
14013185392 | Validate USB devices hot plug check pre and post S0i3(Disconnected Modern Standby) cycle with devices connected on Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sphy,fw.ifwi.tbt | 22012118923 | Y | PASSED | mrajan2x
14013185728 | Validate USB2 HUB Functionality check in BIOS over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch | 22012112638 | Y | PASSED | bajanthx
14013185729 | Validate USB2 HUB Functionality check in EFI over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch | 22012112638 | Y | PASSED | bajanthx
14013185824 | Validate USB2/3 HUB Functionality check in OS pre and post S4 , S5 , warm and cold reboot cycles over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch,fw.ifwi.pchc | 22012112742,22012112764 | Y | PASSED | bajanthx
14013185388 | Validate USB2/3 HUB Functionality check in OS pre and post disconnected-MOS cycle over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch,fw.ifwi.pchc,fw.ifwi.pmc |  | Y | PASSED | bajanthx
16014571537 | Validate USB3.2 Gen2x1 Self-Powered Hub functionality after S3 warm and cold boot cycles | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 1508914416,22012120035 | Y | BLOCKED | mrajan2x | other; CLID- 10582
16013342192 | Validate USB3.2 Gen2x1 Self-Powered Hub functionality after S4.S5.warm and cold boot cycles' | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 1508914416,22012120035 | Y | BLOCKED | mrajan2x | other; CLID- 10582
14013163390 | Validate USB4 Dock Device functionality after S4,S5, warm and cold boot cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106964,22012113968,22012116031 | Y | PASSED | mrajan2x
14013163393 | Validate USB4 Dock Device functionality hot plug during S4, S5 cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 13010026762,22012112720,22012112972,22012113968,22012116031 | Y | PASSED | mrajan2x
14013163402 | Validate USB4 Dock Device functionality on cold plug | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106964,22012112200,22012113968,22012116031 | Y | PASSED | mrajan2x
14013163371 | Validate USB4 Dock Device functionality on hot insert and removal | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106964,22012112200,22012113968,22012115901,22012116031 | Y | PASSED | mrajan2x
14013163332 | Validate USB4 Hub Device functionality after S4, S5, warm and cold boot cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106964,22012113968,22012116031 | Y | PASSED | bajanthx
14013163339 | Validate USB4 Hub Device functionality hot plug during S4, S5 cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012113968,22012116031 | Y | PASSED | bajanthx
14013163359 | Validate USB4 Hub Device functionality on cold plug | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106964,22012112200,22012113968,22012116031 | Y | PASSED | bajanthx
14013163315 | Validate USB4 Hub Device functionality on hot insert and removal | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106578,22012112200,22012113968,22012115901,22012116031 | Y | PASSED | bajanthx
14013160631 | Validate Wi-Fi Network Connectivity by self and External ping | PASSED | connectivity | bios.pch | bios.pch | 13010148297,16018656030,22012110224,22012110363,22012113871 | Y | PASSED | aiyyapax
14013160756 | Validate data transfer functionality between USB drives connected over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 22012111472,22012112808,22012112860,22012118923,22012120025,22012120027,22012134022 | Y | PASSED | deivasix
14013121252 | Validate digital audio functionality over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 22012111472,22012112808,22012112860,22012118923,22012120025,22012120027,22012134022 | Y | PASSED | deivasix
14013184742 | Validate system achieves more than 80% S0i3(CMS) residency | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012110384 | Y | PASSED | mrajan2x
14013158550 | Validate system residency for SLP_S0 in CMS with system in AC mode | PASSED | power_management | bios.platform | bios.platform | 22012110384,22012113180 | Y | PASSED | usavithx
14013162869 | Validate the CPU ID information is captured in Debug logs | PASSED | processor_core | bios.platform | bios.platform | 22012118912,22012615614 | Y | PASSED | deivasix
14013175738 | Verification of SPI Initialization | PASSED | io_general.spi | bios.platform | bios.pch,bios.platform | 18025185648,22012112143,22012134011 | Y | PASSED | bajanthx
14013184823 | Verification of hot keys (F2 & F7) functionality check while BOOT | PASSED | reset | bios.platform | bios.platform,fw.ifwi.bios |  | Y | PASSED | aiyyapax
14013174476 | Verification of resolution for 5K display panel in Pre-OS | BLOCKED | display | bios.platform | bios.platform | 22012113927 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013177238 | Verification on enumeration of PCIe NAND devices connected | PASSED | storage | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | jmanigax
14013178001 | Verify "PCH Energy Reporting" enabled as a default in the BIOS | PASSED | power_management | bios.pch | bios.pch | 14017315200,16019434344,22012134509 | Y | PASSED | mrajan2x
16019543377 | Verify Crahlog Feature is enabled by default in BIOS setup | PASSED | debug | bios.platform | bios.platform | 14017309851 | Y | PASSED | mrajan2x
16013021252 | Verify MEM_CONFIG_DONE from the Bios logs. | PASSED | memory | bios.mem_decode | bios.mrc_client | 22012120321,22013705637 | Y | PASSED | sksharax
14013169128 | Verify MRC training when 2xRefresh is Disabled and Hardware RHP is Enabled | PASSED | memory | bios.mrc_client | bios.mrc_client | 13010548233,14017148479,14017545321,22012119774,22016709004,22017727273 | Y | PASSED | sksharax
14013169126 | Verify MRC training with 2xRefresh is Enabled | PASSED | memory | bios.mrc_client | bios.mrc_client | 14017148479,14017545321,22012116581,22012119774,22012755833,22017727273 | Y | PASSED | sksharax
16019526540 | Verify Removal FFU(Full Flash update) BIOS option from setup page | PASSED | io_general.flash | bios.platform | bios.platform | 16019380426 | Y | PASSED | mrajan2x
14013163226 | Verify Type-C USB3.1 gen2 device enumeration over Type-C port with Retimer Compliance mode Enable/Disable | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 22012115727,22012116026,22012118923,22012120523 | Y | PASSED | mrajan2x
14013176415 | Verify "PCH Trace Hub Enable Mode" BIOS policy/option for NPK Support | PASSED | debug | bios.platform | bios.platform | 22012110414,22012110459,22012111493,22012112262,22012112304,22012113219 | Y | PASSED | mrajan2x
16014934572 | Verify "PCH and CPU Trace Hub Enable Mode" BIOS policy/option for NPK Support when option is disabled | PASSED | debug | bios.platform | bios.platform | 22012112262,22012112292,22012112304,22012133346 | Y | PASSED | usavithx
14013156718 | Verify "Password Policy" is set to "Any Time" under MEBx Setup option in BIOS | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 18014968941,22012119592 | Y | PASSED | sksharax
14013160446 | Verify "Platform Debug Consent" BIOS option/policy | PASSED | debug | bios.platform | bios.platform | 15010285422,16014304365,22012107638,22012112228,22012112252,22012112307,22012112377,22012112394,22012115971 | Y | PASSED | usavithx
14013172908 | Verify "Slide to shutdown" option does not come up on UI on resuming from CMS / S0i3 | PASSED | power_management | bios.platform | bios.platform,fw.ifwi.pmc | 22012110173 | Y | PASSED | agujjarx
14013161111 | Verify 3.5mm jack Wired headphones/headset detection after abrupt G3 | PASSED | audio | bios.platform | bios.pch |  | Y | PASSED | deivasix
14013161102 | Verify 3.5mm jack Wired headphones/headset detection on Pre and Post S0i3 (Modern Standby) cycle | PASSED | audio | bios.platform | bios.pch,fw.ifwi.pchc |  | Y | PASSED | deivasix
14013179162 | Verify 3.5mm jack Wired headphones/headset detection on Pre and Post S4, S5, warm and reboot cycles | PASSED | audio | bios.pch | bios.pch | 15011208676 | Y | PASSED | deivasix
14013164115 | Verify 40 Gbps CIO Link speed for USB4 Storage | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012113968 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013163931 | Verify 40 Gbps Link speed for TBT3 device on hot plug | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa |  | Y | PASSED | mrajan2x
14013187934 | Verify 4K Display Monitor functionality over USB type-C port and connector reversibility' | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 1508914416,22012110433,22012111472,22012112063,22012112808,22012112860,22012134022 | Y | PASSED | mrajan2x
16013677281 | Verify 8K Display Panel enumeration in Device Manager with CMS cycles | BLOCKED | display | bios.platform | bios.platform |  | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16013252950 | Verify ACE enumeration in EFI Shell | PASSED | audio | bios.platform | bios.pch,fw.ifwi.ace,fw.ifwi.others,fw.ifwi.pchc | 16018282839,16018848709 | Y | PASSED | deivasix
14013174344 | Verify ACPI Id of Audio DSP Device in ACPI dump | PASSED | audio | bios.platform | bios.pch | 22012112557 | Y | PASSED | deivasix
14013158359 | Verify ACPI table for S0ix Support | PASSED | system | bios.platform | bios.cpu_pm,bios.sa | 22012112231,22012116661 | Y | PASSED | mrajan2x
16012980309 | Verify AET trace options for processor trace feature | PASSED | debug | bios.pch | bios.pch,bios.sa | 22012118994 | Y | PASSED | mrajan2x
14013180406 | Verify AMT connectivity Provision/Unprovision with static IP using WebUI | PASSED | manageability | bios.me | bios.me | 22012113951,22012114121 | Y | PASSED | usavithx
14013161454 | Verify AMT storage redirection should support for TBT vPro dock | BLOCKED | manageability | bios.me | bios.me | 14014305579,14014407245,22012113855,22012620684 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013185503 | Verify Analog Microphone test connected to 3.5 mm Port pre and post CMS/S0i3 cycle | PASSED | audio | bios.platform | bios.pch,fw.ifwi.pmc |  | Y | PASSED | deivasix
14013174768 | Verify Audio Play back on USB-Headset post S3 cycle | PASSED | audio | bios.platform | bios.pch,fw.ifwi.pchc,fw.ifwi.pmc | 1509172672 | Y | PASSED | deivasix
14013174775 | Verify Audio Play back on USB-Headset pre and post S0i3(Modern Standby) cycle | PASSED | audio | bios.platform | bios.pch,fw.ifwi.bios,fw.ifwi.pchc | 1509172672 | Y | PASSED | deivasix
14013179142 | Verify Audio Play back on USB-Headset pre and post S4 and S5 cycle | PASSED | audio | bios.pch | bios.pch,fw.ifwi.bios,fw.ifwi.pmc |  | Y | PASSED | deivasix
14013176151 | Verify Audio device is enumerated as PCI device | PASSED | io_pcie | bios.pch | bios.pch,bios.platform | 22012112104,22012112104,22012112583 | Y | PASSED | bajanthx
14013185356 | Verify Audio recording and Playback over 3.5mm-Jack-Headset (via HD-A) pre and post S0i3(Modern Standby) cycle | PASSED | audio | bios.platform | bios.pch,fw.ifwi.bios,fw.ifwi.pmc | 1509172672,14014437761,16013146685,16013867625,16015119195 | Y | PASSED | deivasix
16017088502 | Verify BIOS PSF configuration for MTL-S - MTP-S PCH | BLOCKED | reset | bios.pch | bios.pch | 22012118794 | Y | BLOCKED | usavithx | other;
16013307746 | Verify BIOS configures SPI DMA in MTP-S post MRC | PASSED | memory | bios.mrc_client | bios.mrc_client | 22012120920 | Y | PASSED | deivasix
14013176869 | Verify BIOS detects PCIe device connected over X1 slot without remapping the same | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | jmanigax
14013176861 | Verify BIOS display an option to set Detect timeout value on Root port links | PASSED | io_pcie | bios.pch | bios.pch | 22012118481 | Y | PASSED | bajanthx
16012963869 | Verify BIOS exposes the Setup option "Acoustic Context Awareness (ACA)" and HD Audio functionality works fine in OS' | PASSED | audio | bios.pch | bios.pch | 14013637748,22012109485 | Y | PASSED | deivasix
14013156720 | Verify BIOS integrated MEBx menu is not exposed with Consumer BIOS with Vpro supported Silicon | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 18014968941,22012119592 | Y | PASSED | sksharax
16016916848 | Verify BIOS option "Intel(R) Dynamic Tuning Configuration" setting allow 32 bit value input | PASSED | thermal_management | bios.platform | bios.platform | 22014075721 | Y | PASSED | mrajan2x
14013178927 | Verify BIOS provide DDR-RFIM feature enable/disable status via MCHBAR | PASSED | connectivity | bios.pch | bios.pch | 13010148297,22012117495,22012117885,22012118876 | Y | PASSED | aiyyapax
16017785220 | Verify BIOS provide controlled option to disable PROCHOT demotion algorithm | PASSED | thermal_management | bios.cpu_pm | bios.cpu_pm | 22015258606 | Y | PASSED | bajanthx
14013177401 | Verify BIOS reports PS_ON feature status via ACPI method | BLOCKED | power_management.power_mgmt_cntrl | bios.cpu_pm | bios.cpu_pm,bios.pch |  | Y | BLOCKED | deivasix | feature_not_yet_enabled; Need update from Debug DO.
14013176958 | Verify BIOS set up option to enable/Disable GPIO Pad | PASSED | io_general.lsio_gpio | bios.iio | bios.pch,bios.platform,fw.ifwi.bios | 18025337918,18025343764,22012110170,22012112662,22012113265,22012113294,22012113294,22012113698,22012116980 | Y | PASSED | mrajan2x
16012676183 | Verify BIOS sets "INF_DFx_BIOS_EN" policy Via Pcode MAILBOX | PASSED | reset | bios.sa | bios.sa | 22012116434,22015437478 | Y | PASSED | usavithx
14013162515 | Verify BIOS settings remains intact with G3 mode booting after Sx cycles | PASSED | reset | bios.platform | bios.platform |  | Y | PASSED | aiyyapax
16015879097 | Verify BIOS setup Default option for the GPE1 support. | PASSED | io_usb.type_c_subsystem | bios.platform | bios.sa | 14015470869,16017434954 | Y | PASSED | sksharax
14013156692 | Verify BIOS shall display an option to set the IP address and port number of the Intel AMT provisioning server under MEBx menu. | PASSED | manageability | bios.me | bios.me | 18014968941,22012114014,22012119592 | Y | PASSED | sksharax
14013161630 | Verify BIOS shall provide support to add new Bluetooth SAR tables (BRDS) and GPC Method' | PASSED | connectivity | bios.pch | bios.pch | 22012113750 | Y | PASSED | aiyyapax
14013161629 | Verify BIOS shall provide support to add new Switched Antenna Diversity Selection (SADS) field to BIOS configuration' | PASSED | connectivity | bios.pch | bios.pch | 13010148297,16017538025,22012113750 | Y | PASSED | aiyyapax
14013161623 | Verify BIOS shall provide the support to publish the CNVi WIFI and BT UEFI variables with connectivity platform configurations | PASSED | connectivity | bios.pch | bios.pch | 13010148297,16012893395,22012111077,22012113737 | Y | PASSED | aiyyapax
14013164746 | Verify BIOS support for [CNV] New ACPI table WPFC - Wi-Fi PHY Filter Configuration | PASSED | connectivity | bios.pch | bios.pch | 13010148297,22012106513 | Y | PASSED | aiyyapax
14013163101 | Verify BIOS to implement DSM to enable UAOL workaround | PASSED | audio | bios.platform | bios.pch | 15011253417,22012107723 | Y | PASSED | deivasix
14013165037 | Verify BIOS to update post codes on punit register | PASSED | power_management | bios.sa | bios.sa | 22012106637 | Y | PASSED | bajanthx
14013177900 | Verify BIOS updates the PCIe register for PEG60 | BLOCKED | io_pcie | bios.sa | bios.sa | 22012107680,22012108733,22012108789,22012108789,22012117827 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16020035185 | Verify BT headphone device controller information with integrated BT module | PASSED | connectivity.bluetooth | bios.pch | bios.pch,bios.platform | 13010469388 | Y | PASSED | aiyyapax
14013157462 | Verify Bios configured Power Limit 4 | BLOCKED | power_management | bios.cpu_pm | bios.cpu_pm | 1308456131,1308496638,1308604975,1308610053,1308634918,1308713476,1308808317,1308854054,1308914777,1308956112,1309039564,1309149358,14017220675,16012654949,16012801419,16016360441,16018749958,18015216769,22012106827,22012106898,22012117335,22012117341,22012117592,22012117654,22012119255,22012120892,22012133147,22012133160,22012134659,22012780257 | Y | BLOCKED | mrajan2x | awaiting_silicon; cTDP silicon is not available
14013156882 | Verify Bios gives an option to configure Intel Processor Trace Feature(RTIT) | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012107746,22012113879 | Y | PASSED | mrajan2x
14013177299 | Verify Bios have option to Enable/Disable On-board Components | PASSED | system | bios.pch | bios.pch,bios.platform | 22012134002 | Y | PASSED | usavithx
14013177439 | Verify Bios locks TCO_BASE by writing to specific TCO_BASE_LOCK | FAILED | system | bios.pch | bios.pch,bios.platform | 15012622627 | Y | FAILED | mrajan2x
16012975448 | Verify Bios option to enable and Disable the UAOL (USB AUDIO OFFLOAD) | PASSED | io_usb | bios.platform | bios.pch | 1309445130,15011253417,22012542829 | Y | PASSED | usavithx
14013176948 | Verify Bios shall support enable/disable PCIE ports options | PASSED | io_pcie | bios.pch | bios.pch | 1508914138,22012110170,22012110692,22012115964,22012118481 | Y | PASSED | bajanthx
14013160614 | Verify Bluetooth BLE Devices scan in BIOS | PASSED | connectivity | bios.pch | bios.pch | 16014680846,16016399202,16017207453,16017538025,22012106618,22012110363,22012112618,22012118615,22012118738,22012118870 | Y | PASSED | aiyyapax
14013161693 | Verify Bluetooth BLE supported HID device Functionality in OS | PASSED | connectivity | bios.pch | bios.pch | 14018217006,16014680846,16017538025,22012106618,22012110363,22012112441,22012112618 | Y | PASSED | aiyyapax
14013157777 | Verify Bluetooth BLE supported HID device Functionality in OS when no USB devices connected to SUT. | PASSED | connectivity.bluetooth | bios.pch | bios.pch | 16017538025,22012116363 | Y | PASSED | aiyyapax
14013172956 | Verify Boot to OS from NVMe Storage | PASSED | storage | bios.pch | bios.pch,fw.ifwi.bios,fw.ifwi.others | 14014363246,14015515688,22012107657,22012112380,22012112392,22012116651,22012116955,22012118947,22012119295,22012521779 | Y | PASSED | jmanigax
14013160620 | Verify Booting over Wi-Fi using UEFI HTTPv4 Boot | BLOCKED | connectivity | bios.pch | bios.pch | 13010148297,22012106464,22012112399,22012112441 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013179479 | Verify Booting over Wi-Fi using UEFI PXEv6 Boot | BLOCKED | connectivity | bios.pch | bios.pch | 13010148297,22012112401,22012112618 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013163080 | Verify Bus0 Devices with function disabled in bios setup using PEP bios checker tool | BLOCKED | power_management.modern_standby | bios.cpu_pm | bios.cpu_pm,bios.platform | 22012112731,22012113168,22012113687,22012115020,22012115431 | Y | BLOCKED | mrajan2x | other; Sent mail to Domain Owner
14013157183 | Verify C-state residencies during Connected Modern Standby/S0i3 with system in AC mode | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012113420,22012113739,22012118728 | Y | PASSED | usavithx
14013157534 | Verify C-states (_CST) gets defined as part of ACPI dump | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012111962 | Y | PASSED | mrajan2x
14013157757 | Verify CNVi BT/ WiFi enumeration in the device manager when BT/WiFI core enabled and disabled in the setup ' | PASSED | connectivity | bios.pch | bios.pch | 13010148297,16017538025,22012106933 | Y | PASSED | aiyyapax
14013185710 | Verify CNVi Bluetooth Enumeration in OS before/after S3 cycle | FAILED | connectivity | bios.pch | bios.pch | 14015207584,16017538025 | Y | FAILED | aiyyapax
14013160689 | Verify CNVi WLAN Enumeration in OS before / after Connected Standby (CMS) cycle | PASSED | connectivity | bios.pch | bios.pch | 1308732185,13010148297,14015207584 | Y | PASSED | aiyyapax
14013164082 | Verify CNVi WLAN Enumeration in OS before / after warm reset cycle | PASSED | connectivity | bios.pch | bios.pch | 1308732185,13010148297 | Y | PASSED | aiyyapax
14013185694 | Verify CNVi WLAN Enumeration in OS before/after S3 cycle | FAILED | connectivity | bios.pch | bios.pch | 1308732185,13010148297 | Y | FAILED | aiyyapax
14013179118 | Verify CNVi WLAN Enumeration in OS pre and post S4 , S5 , warm and cold reboot cycles | PASSED | connectivity | bios.pch | bios.pch,fw.ifwi.pchc,fw.ifwi.pmc | 1308732185,13010148297,22012113774,22012113912 | Y | PASSED | aiyyapax
14013178765 | Verify CPU Attached storage device detection in BIOS Through VMD | PASSED | storage | bios.cpu_pm | bios.cpu_pm,fw.ifwi.bios |  | Y | PASSED | aiyyapax
14013163063 | Verify CPU enters C10 after removal of USB disk used as source for Music playback in Modern Standby | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | BLOCKED | deivasix | feature_not_yet_enabled;
14013157340 | Verify CPU enters C10 state irrespective of PS_ON status | PASSED | power_management | bios.platform | bios.platform | 22012116487 | Y | PASSED | mrajan2x
14013156881 | Verify CPU switches between all P-states when Number of P states set to 0 | FAILED | power_management | bios.cpu_pm | bios.cpu_pm,fw.ifwi.others,fw.ifwi.pmc | 22012110356,22012111902 | Y | FAILED | usavithx
14013173200 | Verify CPU turbo boost functionality pre and post S4 , S5 , warm and cold reboot cycles | PASSED | power_management | bios.cpu_pm | bios.cpu_pm,fw.ifwi.pmc | 22012110366 | Y | PASSED | usavithx
14013185276 | Verify CPU turbo boost functionality post CMS/S0i3 cycle | FAILED | power_management | bios.cpu_pm | bios.cpu_pm,fw.ifwi.pmc | 22012110366 | Y | FAILED | usavithx
14013183384 | Verify CPU turbo boost functionality post S3 cycle | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012110366 | Y | PASSED | mrajan2x
14013162551 | Verify CSME change from MKHI agent to MCHI agent | PASSED | manageability | bios.me | bios.me |  | Y | PASSED | sksharax
16016576054 | Verify CSME platform ID with UPID feature enabled IFWI | PASSED | manageability | bios.me | bios.me |  | Y | PASSED | sksharax
14013157212 | Verify Chipset information displayed in BIOS | PASSED | processor_core | bios.pch | bios.pch | 14015427057,16014069146,22012112107,22012120931 | Y | PASSED | deivasix
14013165202 | Verify Concurrent DP Display functionality on hot plug over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | mrajan2x
14013165225 | Verify Concurrent HDMI Display functionality on hot plug over Type-C port and Connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | mrajan2x
14013165287 | Verify Concurrent TBT3 Display and Type-C Dock with DP Display functionality on hot plug over Type-C port and Connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa |  | Y | PASSED | deivasix
14013165290 | Verify Concurrent TBT3 Display and Type-C Dock with HDMI Display functionality on hot plug over Type-C port and connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa |  | Y | PASSED | deivasix
14013165243 | Verify Concurrent Type-C Display and DP Display functionality on hot plug over Type-C port and connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | deivasix
14013165260 | Verify Concurrent Type-C Display and HDMI Display functionality on hot plug over Type-C port and connector revresibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | deivasix
14013165272 | Verify Concurrent Type-C Display and Type-C Dock with DP Display functionality on hot plug over Type-C port and Connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | deivasix
14013165281 | Verify Concurrent Type-C Display and Type-C Dock with HDMI Display functionality on hot plug over Type-C port and Connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | deivasix
14013165116 | Verify Concurrent Type-C Display functionality on cold plug over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | mrajan2x
14013165112 | Verify Concurrent Type-C Display functionality on hot plug over Type-C port and Connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012118923 | Y | PASSED | mrajan2x
14013165295 | Verify Concurrent USB3.1-Gen2-SSD and TBT3 Display functionality on hot plug over Type-C port and Connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012112708 | Y | PASSED | deivasix
14013157385 | Verify Core and Threads in BIOS when 1 core is enabled in Hexa Core SKUs | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157383 | Verify Core and Threads in BIOS when 2 cores are enabled in Hexa Core SKUs | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157389 | Verify Core and Threads in BIOS when 3 cores are enabled in Hexa Core SKUs | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157390 | Verify Core and Threads in BIOS when 4 cores are enabled in Hexa Core SKUs | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157392 | Verify Core and Threads in BIOS when 5 cores are enabled in Hexa Core SKUs | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157381 | Verify Core and Threads in BIOS when ALL cores are enabled in Hexa Core SKUs | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013178947 | Verify DMIC basic functionality test over High Definition Audio (HDA) Codec | PASSED | audio | bios.pch | bios.pch | 13010242921,15011208676,16013146685,16013867625,16014658928,16015119195,18022968575 | Y | PASSED | deivasix
14013178956 | Verify DMIC basic functionality test over High Definition Audio (HDA) Codec, pre and post CMS cycles | PASSED | audio | bios.pch | bios.pch | 14014437761,16013146685,16013867625,16014658928,16015119195,22012118728 | Y | PASSED | deivasix
14013158399 | Verify DP display & USB Keyboard functionality over USB Type-C port during Pre and Post boot | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012110433,22012111472,22012112063,22012112808,22012112860,22012115587,22012118923,22012134022,22012947530 | Y | PASSED | deivasix
14013179108 | Verify DP/mini DP panel display in BIOS Setup, EFI and OS | PASSED | display | bios.platform | bios.platform | 15012861566 | Y | PASSED | mrajan2x
14013162548 | Verify Debug log for no Heci Timeout | PASSED | manageability | bios.me | bios.cpu_pm | 15012752267 | Y | PASSED | sksharax
14013156772 | Verify Deepest S0ix State ,SLP_S0 & Package C states with USB Type A Port | PASSED | io_usb | fw.ifwi.platform | bios.pch,fw.ifwi.pchc |  | Y | PASSED | bajanthx
14013179000 | Verify Device Manager for yellow bang and USB storage re-enumeration status during Sx cycle | FAILED | io_usb | bios.pch | bios.pch | 22012109120 | Y | FAILED | bajanthx
14013163415 | Verify Display Functionality over USB4 Dock Device when SUT is in BIOS, EFI and OS level | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106578,22012112200,22012113968,22012115901,22012116031,22015215167 | Y | PASSED | mrajan2x
14013175416 | Verify Display detection and resolution check in post OS with 5K display panel | BLOCKED | display | bios.platform | bios.platform | 22012113927 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013174447 | Verify Display detection in EFI shell with 5K display panel | PASSED | display | bios.platform | bios.platform | 22012113886,22012113927 | Y | PASSED | bajanthx
14013186956 | Verify Domain Name" and HostName" could be set successfully in MEBx setting" | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113951,22012114041,22012114148 | Y | PASSED | sksharax
14013178130 | Verify Dual Tau Feature writing MMIO values With cTDp & Non- cTDP Part | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012115784,22014341926 | Y | PASSED | mrajan2x
1508849790 | Verify Extended bios region Before/After 10 Reboot cycles' | PASSED | reset | bios.platform | bios.platform | 14014825821 | Y | PASSED | aiyyapax
1508850388 | Verify Extended bios region in debug logs' | PASSED | reset | bios.platform | bios.platform | 14014825821 | Y | PASSED | aiyyapax
14013114837 | Verify Fan rotation speed at the time of temperature crosses active trip point during OS hung conditio | BLOCKED | thermal_management | bios.cpu_pm | bios.cpu_pm | 22012115746 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013115136 | Verify GBe/LAN PHY revision is displayed correctly in BIOS Setup | PASSED | connectivity.ethernet | bios.pch | bios.pch | 1309772248,22012112481,22012113341 | Y | PASSED | jmanigax
14013176541 | Verify GNA Configuration menu BIOS options | PASSED | legacy | bios.cpu_pm | bios.pch,bios.platform | 22012110174 | Y | PASSED | sksharax
14013162852 | Verify GPE event triggered in ACPI during ACPI wake alarm test in hibernate | PASSED | power_management | bios.platform | bios.platform |  | Y | PASSED | mrajan2x
22011834621 | Verify GPE event triggered in ACPI during ACPI wake alarm test in sleep state | PASSED | power_management | bios.platform | bios.platform | 22012117536 | Y | PASSED | mrajan2x
14013176789 | Verify GPIO driver and device entry in device Manager | PASSED | io_general.lsio_gpio | bios.iio | bios.pch,bios.platform | 16019013827,18025337918,18025343764,22012112126 | Y | PASSED | mrajan2x
14013177947 | Verify Gen1 to Gen4 speed check with PCIe Gen3 NVMe SSD connected over PCIe Gen4 supported X16 slot | PASSED | audio | bios.pch | bios.cpu_pm | 22012118923 | Y | PASSED | deivasix
14013177672 | Verify Gen1 to Gen4 speed check with PCIe Gen3 NVMe SSD connected over PCIe M.2 Gen4 slot | PASSED | storage | bios.pch | bios.pch | 22012116974 | Y | PASSED | bajanthx
14013177687 | Verify Gen1 to Gen4 speed check with PCIe Gen4 NVMe SSD connected over PCIe Gen4 supported X4 slot | FAILED | storage | bios.pch | bios.pch |  | Y | FAILED | jmanigax | CAT ERROR OBSERVED NVMe connected to x4 sot
14013178329 | Verify Gen1 to Gen5 speed check with PCIe Gen3 NVMe SSD connected over PCIe Gen5 supported X16 slot | PASSED | io_pcie | bios.sa | bios.cpu_pm,bios.sa | 22012111392 | Y | PASSED | usavithx
14013178330 | Verify Gen1 to Gen5 speed check with PCIe Gen4 NVMe SSD connected over PCIe Gen5 supported X16 slot | PASSED | io_pcie | bios.sa | bios.cpu_pm,bios.sa | 22012111392,22012117296 | Y | PASSED | bajanthx
14013179168 | Verify HD Display Audio (Intel Display Audio) enumeration pre and post S4, S5, warm and cold reboot cycles | PASSED | audio | bios.platform | bios.pch,fw.ifwi.bios,fw.ifwi.pmc | 22012112626 | Y | PASSED | deivasix
14013185372 | Verify HD Display Audio enumeration pre and post CMS cycle | PASSED | audio | bios.platform | bios.pch,fw.ifwi.pmc | 22012112626 | Y | PASSED | deivasix
14013160568 | Verify HDCP 2.2 functionality over TBT port | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt |  | Y | BLOCKED | deivasix | missing_inventory; HDCP 2.2 Monitor Not Availble
14013160571 | Verify HDCP 2.2 functionality over TBT port after Sx and warm reboot cycles | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt |  | Y | BLOCKED | deivasix | missing_inventory; HDCP 2.2 Monitor Not Available
14013177396 | Verify HID driver event filter driver from BIOS menu for non-mobile platforms | PASSED | system | bios.pch | bios.pch,bios.platform |  | Y | PASSED | jmanigax
16016240713 | Verify HWID for ICCWDT in device manager | PASSED | io_general | bios.platform | bios.platform | 16015354904,16018275832 | Y | PASSED | mrajan2x
14013173177 | Verify Hibernate, Shutdown entry and exit via power butto | PASSED | power_management | bios.platform | bios.platform | 22012110321,22012112849,22012113274 | Y | PASSED | agujjarx
14013175736 | Verify Hiding NVMe interface on PCIe bus | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | jmanigax
16016730215 | Verify IA Exclusion CCF support registers are programmed | PASSED | reset | bios.sa | bios.sa | 22012118165 | Y | PASSED | aiyyapax
14013185811 | Verify IDTT (DPTF) devices enumeration in device manager pre and post S4,S5, warm and cold reboot cycles | PASSED | power_management.thermal_sensor | bios.platform | bios.platform,fw.ifwi.tools | 22012110437,22012111977,22012113523,22012116787,22014341926 | Y | PASSED | sksharax | verified with available Sensors
16017293161 | Verify IMR base address does get initialized after Mask/Limit, RAC and WAC | PASSED | reset | bios.sa | bios.sa | 14016720988 | Y | PASSED | aiyyapax
14013179183 | Verify Intel HD Audio functionality over 3.5mm Jack Speakers pre and post S4, S5, warm and cold reboot cycles | PASSED | audio | bios.pch | bios.pch,fw.ifwi.bios,fw.ifwi.pmc |  | Y | PASSED | deivasix
14013157260 | Verify Intel(R) Dynamic Tuning technology/Intel(R) Innovation Platform Framework support enabled in BIOS for DT SKUs | PASSED | thermal_management | bios.cpu_pm | bios.cpu_pm | 22014341926 | Y | PASSED | bajanthx
14013180605 | Verify KVM session can be established When SUT is in MEBX Menu and BIOS Menu | FAILED | manageability | bios.me | bios.me | 22012113806 | Y | FAILED | usavithx
16017995481 | Verify Keep Early Trace BIOS setup option when PDC setup option is set to "Enable-High Power" | PASSED | debug | bios.pch | bios.pch | 15011478382,16014304365 | Y | PASSED | mrajan2x
14013158254 | Verify Legacy USB devices (Pendrive, Mouse and Keyboard) functionality over TBT port after S3 ,S4 and S5 Cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt |  | Y | PASSED | deivasix
14013165567 | Verify Link speed-40 Gbps for TBT4 device after sx cycle | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 13010026762 | Y | PASSED | bajanthx
14013165574 | Verify Link speed-40 Gbps for TBT4 device during sx cycle | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 13010026762 | Y | PASSED | bajanthx
14013165569 | Verify Link speed-40 Gbps for TBT4 device on cold plug | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 13010026762 | Y | PASSED | bajanthx
14013165562 | Verify Link speed-40 Gbps for TBT4 device on hot plug | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 13010026762 | Y | PASSED | bajanthx
14013156716 | Verify Local FW Updates option is available in BIOS Setup | PASSED | manageability | bios.me | bios.me | 18014968941,22012119592 | Y | PASSED | sksharax
14013186951 | Verify Local FW Updates option is available in MEBx /BIOS Setup | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113527,22012113951,22012114088 | Y | PASSED | sksharax
14013180382 | Verify Local FW Updates option is available in MEBx /BIOS Setup' | PASSED | manageability | bios.me | bios.me | 22012113527,22012113951,22012114088 | Y | PASSED | sksharax
22011834534 | Verify ME un-configuration using Bios optio | PASSED | manageability | bios.me | bios.me |  | Y | PASSED | sksharax
14013187021 | Verify ME(M0) status pre and post cold and warm reset cycle | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113762,22012113891 | Y | PASSED | usavithx
14013165425 | Verify MEBx Menu should not Present in BIOS on Consumer SKU IFWI | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme |  | Y | PASSED | sksharax
16016018054 | Verify MRC for Mem training with different memory configurations | PASSED | memory | bios.mrc_client | bios.mrc_client | 14017545321 | Y | PASSED | deivasix
16017748989 | Verify MRC training with Multi channel and Multi Rank modules connected | PASSED | memory | bios.mrc_client | bios.platform | 1309796337 | Y | PASSED | sksharax | VERIFIED WITH AVAILABLE SLOTS
16015997461 | Verify MRC training with different memory topology and Trigger MRC training after multiple reset cycles. | BLOCKED | memory | bios.mrc_client | bios.mrc_client | 14017545321 | Y | BLOCKED | deivasix | feature_not_yet_enabled;
16018492040 | Verify Memory Map Tab for Memory Range not getting corrupted | PASSED | memory | bios.mrc_client | bios.mrc_client,bios.platform |  | Y | PASSED | deivasix
16019847988 | Verify NPHY version in the ME using mFIT | BLOCKED | manageability | bios.manageability | bios.me,bios.pch | 14016352605 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16012980276 | Verify NPK support - one from SOC, one from PCH | BLOCKED | debug | bios.pch | bios.pch,bios.sa | 22012118048,22012118994 | Y | BLOCKED | deivasix | feature_not_yet_enabled;
14013176995 | Verify NVMe functionality over X4 slot across pre and Post Sx cycles | FAILED | storage | bios.pch | bios.pch |  | Y | FAILED | jmanigax | cate error observed nvme is connected to X4 slot
14013177881 | Verify NVMe-SSD achieve SLP_S0 and PC10 Residency with VMD enabled | PASSED | storage | bios.pch | bios.pch | 22012115665 | Y | PASSED | mrajan2x
14013177974 | Verify NVMe-SSD detection in Bios connected to Add-on-card connected over PCIe-X4 Slot | PASSED | storage | bios.pch | bios.pch | 18018859419 | Y | PASSED | jmanigax
14013178387 | Verify NVMe-SSD detection in Bios connected to Add-on-card connected over X16 Gen5 Slot | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | aiyyapax
14013179017 | Verify NVMe-SSD"s detection in Bios & O.S when connected to x4 slots & M.2 slots from CPU & PCH. | PASSED | storage | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | aiyyapax
16019663602 | Verify No YB in device manager post S4 with USB3DBC connected in SUT | BLOCKED | debug | bios.platform | bios.platform | 15012615964 | Y | BLOCKED | mrajan2x | other; CLID-10598
14013182858 | Verify No device yellow bangs post S3/S0i3 cycle with all device connected as per config planned ( Golden, delta, 5, 4, 3 STAR ) | FAILED | reset | bios.platform | bios.platform |  | Y | FAILED | aiyyapax
14013182597 | Verify No device yellow bangs post cold boot cycles with all device connected as per config planned ( Golden, delta, 5, 4, 3 STAR ) | PASSED | power_management | bios.platform | bios.platform,fw.ifwi.bios | 22012108982 | Y | PASSED | mrajan2x
14013177003 | Verify OS installation through Optical disk devices | BLOCKED | storage | bios.pch | bios.pch |  | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013158404 | Verify On-Board Audio ADSP is Functional | PASSED | audio | bios.platform | bios.pch,fw.ifwi.pchc | 22012112557 | Y | PASSED | deivasix
14013185684 | Verify Onboard LAN Enumeration in OS | PASSED | connectivity | bios.pch | bios.pch,fw.ifwi.pchc |  | Y | PASSED | aiyyapax
14013176877 | Verify Options available in the USB configuration page of BIOS Setup | PASSED | io_usb | bios.platform | bios.pch | 22012112200 | Y | PASSED | bajanthx
14013117305 | Verify Options available in the USB configuration page of BIOS Setup (AIO/DT/HALO) | BLOCKED | io_usb | bios.pch | bios.pch | 14014507888,16018013927,22012107686,22012112200 | Y | BLOCKED | usavithx | missing_inventory;
14013174020 | Verify PAVP BIOS option | PASSED | content_protection | bios.sa | bios.sa | 22012113292 | Y | PASSED | aiyyapax
14013163067 | Verify PC10 with TBT Dock Hotplug/unplug after S4 | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt |  | Y | BLOCKED | usavithx | other;
14013163467 | Verify PCH DFx Trace hub support | PASSED | debug | bios.platform | bios.platform | 16014304365,22012109303,22012115971 | Y | PASSED | mrajan2x
14013177167 | Verify PCH PCIe root port MPC bit should not be set if VTd enabled in BIOS | BLOCKED | io_pcie | bios.pch | bios.pch | 22012110481 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013162538 | Verify PD controller Firmware version in BIOS, OS and System Scope Tool | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,fw.ifwi.bios | 15011108945,16018502730,16019239578,22012118923 | Y | PASSED | mrajan2x
14013157740 | Verify PMC static function disable configuration locking | PASSED | power_management | bios.sa | bios.sa | 22012111311 | Y | PASSED | agujjarx
14013161304 | Verify PPIN Feature when SUT is in EOM mode | FAILED | processor_core | bios.cpu_pm | bios.cpu_pm | 22012110335,22012119177 | Y | FAILED | bajanthx
14013177277 | Verify PS_ON Residency with NVMe Storage device | BLOCKED | storage | bios.pch | bios.pch |  | Y | BLOCKED | mrajan2x | missing_inventory; pleasant star NVMe
14013178252 | Verify PS_ON Residency with TypeC device connected to dTBT USBC port | PASSED | io_usb | bios.pch | bios.pch | 22012119805,22012119842 | Y | PASSED | bajanthx
14013175110 | Verify Pkg C-state with SUT idle and display ON | BLOCKED | display | bios.platform | bios.platform |  | Y | BLOCKED | mrajan2x | other; CLID-10365
14013156950 | Verify Platform PL1 and PL2 Bios options | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 1308634918,13010402265,13010417400,22012113389,22012113470,22012113873,22012118400,22012118403,22012118406,22013066411 | Y | PASSED | mrajan2x
14013158482 | Verify Post Codes for Connected Standby entry and exit | PASSED | power_management | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | mrajan2x
16018977782 | Verify Power Floor Control Options in BIOS | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm | 22015075880 | Y | PASSED | sksharax
16013039722 | Verify Provided Memory configuration to display driver through scratchpad register (0:2:0) | FAILED | memory | bios.mem_decode | bios.mrc_client | 22012117780 | Y | FAILED | deivasix
14013161879 | Verify RTD3 flow support for TBT SSD device | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 1308713258,22012106964,22012111466,22012115901,22012116113,22012116500,22012117842 | Y | PASSED | deivasix
14013158813 | Verify RTD3 flow support for Type-C USB3.1 device | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 16017137606,18025116166,22012106964,22012112801,22012113860,22012115169,22012116113,22012118923,22012120025,22012120027,22015102690,22015720747 | Y | PASSED | deivasix
14013179157 | Verify RTD3 support for HD Audio Controller with and without Audio playback | PASSED | audio | bios.pch | bios.platform |  | Y | PASSED | deivasix
16013431292 | Verify RTD3 support with add-on-card on x4 (CEM slot) slot connected with NVMe. | BLOCKED | storage | bios.platform | bios.pch | 22012214700 | Y | BLOCKED | usavithx | other;
14013179021 | Verify Remapped NVMe-SSD"s detection in Bios & O.S when connected to x4 slots & M.2 slots from CPU & PCH. | PASSED | storage | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | aiyyapax
14013162132 | Verify Remote Restart and shutdown on TBT-vPRO Dock | BLOCKED | manageability | bios.me | bios.me | 14014305579,14014407245,22012113855,22012620684 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013159842 | Verify S0ix/CS LED Status | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 1509816498,22012113580,22013215478 | Y | PASSED | mrajan2x
14013173144 | Verify S3 and S4 LED status | PASSED | power_management | bios.platform | bios.platform | 22012113309,22012113551,22012113580,22012120906 | Y | PASSED | agujjarx
14013175525 | Verify SAMedia RC6 Context memory is allocated by BIOS correctly within SA Media WOPCM region | PASSED | graphics | bios.sa | bios.sa | 22012117977 | Y | PASSED | mrajan2x
16017147549 | Verify SBREG3 and EPMASK programmed correctly | BLOCKED | io_general | bios.platform | bios.platform |  | Y | BLOCKED | usavithx | other;
14013178088 | Verify SLP_S0 , Package C states & S0I3.4 with M.2 NVMe connected. | PASSED | storage | bios.pch | bios.pch | 14017622566,22012108522 | Y | PASSED | mrajan2x | verified with S0i2.2
14013121481 | Verify SUT Entry and Exit in CS Low Power Mode | PASSED | power_management.modern_standby | bios.cpu_pm | bios.cpu_pm | 22012113473,22012113637,22012116240,22012120699 | Y | PASSED | usavithx
14013169121 | Verify SUT boots with 2xRefresh/Hardware RHP Enabled/Disabled | PASSED | memory | bios.mrc_client | bios.mrc_client | 22012116581,22012119774,22017727273 | Y | PASSED | sksharax
14013182355 | Verify SUT should be able to boot from USB 3.0 disk over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 22012112720,22012112742,22012112768,22012112972 | Y | PASSED | bajanthx
14013182348 | Verify SUT should be able to boot from USB2 Pendrive over Type-C port | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 22012112750,22012112972,22012118923 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013172888 | Verify SUT shutdown (S5) when the Power Button is held during POWER_ON_TIME with only AC plugged-i | PASSED | reset | bios.pch | bios.pch,fw.ifwi.bios,fw.ifwi.ec,fw.ifwi.pchc |  | Y | PASSED | aiyyapax
14013163434 | Verify SUT wake from S3/S4 using USB device & LAN connected behind USB4 Dock | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106578,22012112972,22012113350,22012113968,22012115901,22012116031,22012133075 | Y | BLOCKED | mrajan2x | missing_inventory; LAN port is not available in USB4 dock
14013177978 | Verify SX cycles with M.2 NVMe-SSD connected to Add-on-card connected over PCIe-X4 Slot | FAILED | storage | bios.pch | bios.pch,fw.ifwi.pmc |  | Y | FAILED | jmanigax | cat error observed Add-on-card connected over PCIe-X4 Slot
14013177993 | Verify SX cycles with NVMe SSD"s connected to M.2 Gen4 slots from CPU & PCH. | PASSED | storage | bios.pch | bios.pch,fw.ifwi.pchc,fw.ifwi.pmc | 22012107111,22012117758 | Y | PASSED | usavithx
14013178532 | Verify SX cycles with NVMe connected to Add-on-card connected over x16 PCIe Gen5 slot | PASSED | storage | bios.cpu_pm | bios.cpu_pm,fw.ifwi.pmc |  | Y | PASSED | bajanthx
14013177988 | Verify SX cycles with NVMe connected to Add-on-card connected over x16 PCIe Gen5 slot | FAILED | storage | bios.pch | bios.pch | 1509817431,16012980174,22012111392,22012118478 | Y | FAILED | jmanigax | YB in s3
14013177968 | Verify SX cycles with NVMe connected to M.2 Gen4 slot | FAILED | storage | bios.cpu_pm | bios.cpu_pm,fw.ifwi.pmc | 22012116651 | Y | FAILED | jmanigax | YB S3 SX cycles
16012695195 | Verify Storages Features Removal. | PASSED | storage | bios.pch | bios.pch | 16014720967,16016328577,16016511805,22012118977 | Y | PASSED | jmanigax
14013156793 | Verify System Boot with "Dual Tau Boost" option Enabled /Disabled Post Sx | BLOCKED | power_management | bios.cpu_pm | bios.cpu_pm | 22012115784,22012119683,22014341926 | Y | BLOCKED | mrajan2x | awaiting_silicon; cTDP silicon is not available
14013156797 | Verify System Boot with "Dual Tau Boost" option Enabled /disabled | BLOCKED | power_management | bios.cpu_pm | bios.cpu_pm | 22012115784,22012119683,22014341926 | Y | BLOCKED | mrajan2x | awaiting_silicon; cTDP silicon is not available
14013172868 | Verify System Memory Details in BIOS (SODIMM) | PASSED | reset | fw.ifwi.ec | bios.pch,fw.ifwi.bios,fw.ifwi.ec,fw.ifwi.pchc | 22012113560,22012113616 | Y | PASSED | aiyyapax
14013161557 | Verify System auto wakes from hibernate via RTC with system in AC mode | PASSED | power_management | bios.platform | bios.platform,fw.ifwi.pmc | 15010922195,22012110378,22012113728,22012114866 | Y | PASSED | mrajan2x
14013177213 | Verify System boot from NVMe device connected in PEG port and stability after Sx cycles | PASSED | storage | bios.pch | bios.pch,fw.ifwi.others,fw.ifwi.pmc |  | Y | PASSED | usavithx
14013178803 | Verify System boot from NVMe device connected in PEG port and stability after Sx cycles Through VMD | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | aiyyapax
14013158321 | Verify System entry to Sx states via command line | FAILED | power_management | bios.platform | bios.platform |  | Y | FAILED | usavithx
14013172875 | Verify System memory using Windows Memory Diagnostics tool (Standard) | PASSED | reset | fw.ifwi.ec | bios.pch,fw.ifwi.bios,fw.ifwi.ec,fw.ifwi.pchc | 22012112805 | Y | PASSED | aiyyapax
14013164359 | Verify System reset without any extra delay when crash feature disabled . | PASSED | debug | bios.platform | bios.platform | 14016749496 | Y | PASSED | mrajan2x
14013114941 | Verify System wakes from C-MoS using USB device connected to USB Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012113290,22012118923 | Y | PASSED | deivasix
14013163281 | Verify TBT Device functionality with TCSS D3 Cold support enabled | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 14017576330,22012106964,22012113860,22012115528,22012119266,22012783959 | Y | PASSED | mrajan2x
14013158689 | Verify TBT Hot-Plug device functionality after CMS cycling | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012119914 | Y | PASSED | deivasix
16013832714 | Verify TBT Storage device enumeration with VMD settings enabled | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 14014234917 | Y | PASSED | mrajan2x
14013159094 | Verify TBT device functionality before/after CMS cycling | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 22012106964 | Y | BLOCKED | deivasix | feature_not_yet_enabled;
16013998932 | Verify TBT/USB4 devices enumeration and and Functionality with SW CM mode enabled | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 1509361852,22012106578,22012106964,22012113968,22012115901 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013159080 | Verify TBT3 enumeration of storage and display devices on hot plug and connector reversibility | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 1508914416,22012106836,22012115587,22012116183 | Y | PASSED | deivasix
14013172940 | Verify Type-C Connector reversibility functionality for Display over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt | 16013184268,22012115725,22012118923,22012120735 | Y | PASSED | deivasix
14013163230 | Verify Type-C USB3.1 gen2 device enumeration over Type-C port after resume from S4, S5 with Retimer Compliance mode Enable/Disable | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.tbt | 22012115727,22012116026,22012118923 | Y | PASSED | mrajan2x
14013164939 | Verify UEFI BIOS shall support protocols to support factory OS boot from RAM | PASSED | reset | bios.mem_decode | bios.mem_decode | 22012120224 | Y | PASSED | aiyyapax
14013159090 | Verify USB 3.1 Gen1 (Type-C) Device functionality in Host Router before/after Sx Cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012111401,22012112708 | Y | PASSED | deivasix
16013028888 | Verify USB Type-A Ports functionalities with CPU TCSS disabled | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012116932 | Y | PASSED | mrajan2x
14013172938 | Verify USB Type-C device Connector reversibility functionality when SUT is in Sx (S3.S4.S5)\r\n state' | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 1508914416,16017137606,22012118923,22012120025,22012120027 | Y | PASSED | usavithx
14013160910 | Verify USB devices information are displayed in F7 boot menu, connected over Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012111472,22012112808,22012112860,22012118923,22012134022 | Y | PASSED | mrajan2x
14013162168 | Verify USB-R Controllers is initialized during boot by verifying Keyboard/Mouse can be used to enter BIOS Setup while Booting SUT from S5 using KVM over TBT-vPRO-Dock | BLOCKED | manageability | bios.me | bios.me | 22012113855 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013163425 | Verify USB4 Storage connection swap during S4, S5 cycle | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012113968,22012120027 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013165121 | Verify USB4 Storage enumeration in EFI shell and BIOS setup | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012106578,22012109658,22012113780,22012113968,22012115901 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16013697548 | Verify USB4 storage functionality after S3 cycles | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106578,22012106964,22012113780,22012115901 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013162847 | Verify USB4 storage functionality after S4,S5, warm and cold boot cycles | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012106228,22012106578,22012106964,22012113968,22012115587,22012115901,22012116031,22012133076,22015215167 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16016882747 | Verify VC mapping for TC/VC for PCIe | BLOCKED | graphics | bios.platform | bios.platform |  | Y | BLOCKED | usavithx | other;
14013178068 | Verify VMD RTD3 support with NVMe connected During Sx cycles | BLOCKED | storage | bios.pch | bios.pch | 14014479807,22012109227,22012134602,22012816450 | Y | BLOCKED | mrajan2x | other; RTD3 D3 cold not asserting
14013178094 | Verify VMD RTD3Cold support with NVMe connected to PCH M.2 slot. | PASSED | storage | bios.pch | bios.pch | 18018800713,22012108522 | Y | PASSED | aiyyapax
14013178085 | Verify VMD RTD3Cold support with add-on-card on x4 slot connected with NVMe. | FAILED | storage | bios.pch | bios.pch | 22012108522,22012111245 | Y | FAILED | jmanigax | Cat error observed add-on-card on x4 slot connected with NVMe.
14013177029 | Verify VMD Register Lock bit when VMD device is not in use | PASSED | storage | bios.cpu_pm | bios.cpu_pm | 22012111143,22012111653,22012112573,22012113247 | Y | PASSED | usavithx
14013177247 | Verify VMD device ID verification in EFI and OS | PASSED | storage | bios.cpu_pm | bios.cpu_pm,fw.ifwi.bios | 16014196779,16018309541,18014809061,22012109666,22012111644 | Y | PASSED | mrajan2x
14013177744 | Verify VMD device ID verification in EFI and OS | BLOCKED | storage | bios.pch | bios.pch | 15010833811,16017778590,22012111245,22012111315,22012116651 | Y | BLOCKED | usavithx | other;
14013178773 | Verify VMD driver version in BIOS HII menu Through VMD | PASSED | storage | bios.pch | bios.pch | 1509187642,13010201784,15010986708,18014809061,18017052424,18017442828,18017738823,18018594847,18020096566,18022677185,18022730591,18025338153,22012106951,22012521779 | Y | PASSED | aiyyapax
14013177249 | Verify VMD enable/disable bit in OS with respect to option set in BIOS | PASSED | storage | bios.cpu_pm | bios.cpu_pm,fw.ifwi.bios | 18014809061,22012107343 | Y | PASSED | mrajan2x
14013177681 | Verify VMD enabled CPU Attached Storage device boot and stability after Sx cycles | PASSED | storage | bios.pch | bios.pch,fw.ifwi.pmc |  | Y | PASSED | jmanigax
14013177652 | Verify VTd support for PCIe ports | BLOCKED | io_pcie | bios.pch | bios.pch |  | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013174718 | Verify Video play back on Extended Mode with eDP+HDMI Display panels connected | PASSED | display | bios.platform | bios.platform | 22012112219,22012114303 | Y | PASSED | mrajan2x
14013175271 | Verify Vision processing unit (VPU) gets exposed as a PCI device | PASSED | artificial_intelligence.vpu | bios.sa | bios.pch | 22012117857,22012134764 | Y | PASSED | deivasix
14013172087 | Verify Volume Management Device (VMD) controller bar registers should initialize at PEI phase | BLOCKED | storage.vmd | bios.platform | bios.platform | 22012111284,22012119186 | Y | BLOCKED | mrajan2x | other; CLID-10356
14013179437 | Verify WLAN and Bluetooth functionality in OS when AirPlane (Flight) Mode switch in On/OFF state | PASSED | connectivity | bios.pch | bios.pch | 13010148297,16017538025,22012110363,22012113964 | Y | PASSED | aiyyapax
14013161809 | Verify Wi-Fi and Bluetooth functionality after Sx(S3, S4, S5) and reboot cycles with RTD3 option enabled in BIOS | FAILED | connectivity | bios.pch | bios.platform | 13010148297,16017538025,22012110363 | Y | FAILED | aiyyapax
16015455092 | Verify _DSD method for D3 with USB3 connected to PCH slot in AHCI mode | BLOCKED | storage | bios.pch | bios.pch,bios.platform | 14015415709 | Y | BLOCKED | usavithx | other;
14013163232 | Verify all Type-C port functionality with debug settings disabled | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012108618,22012118923,22012120025,22012120027 | Y | PASSED | mrajan2x
16017280240 | Verify all the PCIe slots (SOC , IOE & PCH) connected with the devices are enumerating at OS | BLOCKED | io_pcie | bios.platform | bios.platform | 13010001130 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013179255 | Verify basic boot check with different IFWI (Release, Performance and Debug) | PASSED | reset | bios.platform | bios.platform |  | Y | PASSED | aiyyapax
14013165526 | Verify booting support through USB 3.2 Gen2 (SS+ mass storage) connected over USB Type-A port | PASSED | io_usb | bios.pch | bios.pch | 22012112101,22012112720,22012112742,22012118947 | Y | PASSED | bajanthx
14013182324 | Verify booting support through USB 3.2 Gen2 (SS+ mass storage) connected over USB Type-C port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt | 22012112720,22012112742,22012118923,22012118947,22012120025,22012120027 | Y | PASSED | deivasix
14013175598 | Verify correct CPU details displayed in BIOS Setup page | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm | 1308496638,1308665876,1509198006,15012595615,16013601138,22012111388,22012118791 | Y | PASSED | deivasix
14013160085 | Verify detection and enumeration of 3.5mm Jack Wired headphones/headset | PASSED | audio | bios.platform | bios.pch,fw.ifwi.pchc |  | Y | PASSED | deivasix
14013176942 | Verify device defined under VMD should not be detected in PCI line item | PASSED | storage | bios.cpu_pm | bios.cpu_pm | 1508989787,16017778590,22012106951,22012111143,22012111644,22012111653,22012117516,22012117523,22012134279 | Y | PASSED | mrajan2x
14013160449 | Verify different power state changes on Modern standby enabled system | PASSED | power_management | bios.platform | bios.platform,fw.ifwi.pmc | 22012110173,22012112283,22012113476,22012113526,22012113744 | Y | PASSED | mrajan2x
14013186993 | Verify different power state changes on Modern standby enabled system | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 22012114138 | Y | PASSED | sksharax
14013160451 | Verify different power state changes on system post Sleep cycle | FAILED | power_management | bios.platform | bios.platform,fw.ifwi.pmc |  | Y | FAILED | mrajan2x
14013186997 | Verify different power state changes on system post Sleep cycle | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012114035 | Y | PASSED | usavithx
14013165541 | Verify if system support disable/enable of the Crossover Canyon capability | PASSED | manageability | bios.me | bios.me | 22012116061,22012119205,22012119657 | Y | PASSED | deivasix
16013229221 | Verify if BIOS displays correct GT DID (internal graphics) details as per Dynamic graphics branding | PASSED | graphics | bios.sa | bios.mrc_client,bios.sa | 14013486554,16017849100,22012949691 | Y | PASSED | mrajan2x
16013268668 | Verify if BIOS provides an option to switch AMT support from onboard LAN to discrete Foxville LAN | PASSED | manageability | bios.me | bios.me | 1508842166 | Y | PASSED | sksharax
16012661522 | Verify if DMI3BAR is enabled' | PASSED | unclassified | bios.sa | bios.sa | 22012116701 | Y | PASSED | bajanthx
16019358759 | Verify if HECI device interrupt pin is programmed via P2SB register | PASSED | io_general | bios.me | bios.me | 18021198105 | Y | PASSED | mrajan2x
14013157206 | Verify if Intel SelfTest completes successfully | FAILED | processor_core | bios.platform | bios.platform,fw.ifwi.bios | 22012114335 | Y | FAILED | deivasix
16013214329 | Verify if MEBX option is displayed in the BIOS page with ME Corporate SKU | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 22012113825 | Y | PASSED | sksharax
16015025624 | Verify if MEBX screen does not display MEBx version on Integrated MEBx' | PASSED | manageability | bios.me | bios.me | 18018442023,22012114108 | Y | PASSED | sksharax
14013156717 | Verify if MEBx password change is accepted (for password meeting specific criteria) and is successfully accepted on subsequent entries under MEBx menu in BIOS | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 18014968941,22012119592 | Y | PASSED | sksharax
16016062149 | Verify if OEM debug configuration menu is removed from MEbx page | PASSED | manageability | bios.me | bios.me,bios.platform | 16015791474 | Y | PASSED | sksharax
16015984160 | Verify if switching AMT support from onboard LAN to discrete Foxville LAN is not provided with consumer SKU | PASSED | manageability | bios.me | bios.me | 1508842166 | Y | PASSED | sksharax
14013162993 | Verify if system boots in Fast Boot mode with Peg Bifurcation card during S3 cycle | BLOCKED | power_and_perf | bios.platform | bios.platform | 22012111862 | Y | BLOCKED | mrajan2x | missing_inventory; PCIe-GFX-X16-Bifurcation-card
14013166904 | Verify if system boots in Fast Boot mode with Peg Bifurcation card pre and post S4 cycle | BLOCKED | power_and_perf | bios.platform | bios.platform | 22012111862 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16015052880 | Verify if system can not be connected to the host when network is not activated | FAILED | manageability | bios.me | bios.me | 22012114108 | Y | FAILED | usavithx
14013186953 | Verify if user can edit Network Name in MEBx Settings' | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 22012114140 | Y | PASSED | sksharax
16014360983 | Verify inability of activating network access from USB provisioning flow | FAILED | manageability | bios.me | bios.me | 22012114154,22013490130 | Y | FAILED | bajanthx
14013161592 | Verify independent BIOS setup option to Enable/Disable INT3400 Device and Processor thermal device participants | PASSED | thermal_management | bios.cpu_pm | bios.cpu_pm | 22012107125,22012110429 | Y | PASSED | bajanthx
14013162108 | Verify local machine AMT WEBUI is accessible after sx cycles over TBT-vPRO-Dock | BLOCKED | manageability | bios.me | bios.me | 22012113855 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013186891 | Verify local user cannot enter MEBx settings to change Intel Standard Manageability Configuration with Wired LAN, when Storage redirection is active | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012114063 | Y | PASSED | usavithx
14013165053 | Verify multiple global reset functionality cycles check in SUT with Debug BIOS | PASSED | reset | bios.platform | bios.platform |  | Y | PASSED | aiyyapax
16014380710 | Verify new Bios setup option "Crashlog Storage Off' is added for Crash log feature | BLOCKED | debug | bios.platform | bios.platform | 14016749496,14017309851,22013047670 | Y | BLOCKED | usavithx | other;
14013157813 | Verify no errors or failures get registered as part of event viewer log post Sx cycles | PASSED | power_management | bios.platform | bios.platform | 22012110321,22012112283,22012113067,22012113089 | Y | PASSED | mrajan2x
14013179024 | Verify package C10 with CPU attached M.2 NVMe storage Through VMD | PASSED | storage | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | mrajan2x | PC10 - 98.26%, BIOSv_3162_01
14013177665 | Verify package C10 with CPU attached storage | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | mrajan2x
14013177668 | Verify package C10 with PCIe Gen3 NVMe SSD connected over PCIe Gen4 supported X4 slot | FAILED | storage | bios.pch | bios.pch | 22012117758 | Y | FAILED | jmanigax | cat error observed Nvme is connected to X4 slot
14013177835 | Verify package C10 with PCIe NVMe SSD connected over PCH M.2 Slot with VMD port disabled | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | usavithx
14013177828 | Verify package C10 with PCIe NVMe SSD connected over PCIe Gen4 NVME Slot with VMD port disabled | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | usavithx
14013158248 | Verify package c-state residency during CMS if package C state is limited to C10/C9/C8/ in BIOS | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012110173,22012111962,22012121062 | Y | PASSED | usavithx
14013177703 | Verify platform supports Power Loss Notification (PLN) feature for NVMe SSD | PASSED | storage | bios.platform | bios.platform | 22012109699 | Y | PASSED | mrajan2x
14013164345 | Verify platform supports corresponding option in BIOS to enable/disable GPRs in Crash Log data | PASSED | debug | bios.platform | bios.platform | 22012115619 | Y | PASSED | mrajan2x
14013173229 | Verify post code functionality across Sx cycles | PASSED | reset | bios.platform | bios.platform | 22012111843,22012113395,22012113410,22012113655 | Y | PASSED | mrajan2x
14013176969 | Verify setting Detect timeout value in BIOS and ensure no halt message in debug log with device connected | PASSED | io_pcie | bios.pch | bios.pch | 22012118481 | Y | PASSED | bajanthx
14013176972 | Verify setting Detect timeout value in BIOS and respective system halt with device not connected | PASSED | io_pcie | bios.pch | bios.pch | 22012118481 | Y | PASSED | bajanthx
14013162433 | Verify stability of Wi-Fi and BT functionality with ECKV (External Clock Valid) option enabled in BIOS | PASSED | connectivity | bios.pch | bios.platform | 1308785954,13010148297,16017538025,22012106335,22012110424 | Y | PASSED | aiyyapax
14013162422 | Verify stability of Wi-Fi and BT functionality with PPAG (Per Platform Antenna Gain) option enabled in BIOS | PASSED | connectivity | bios.pch | bios.platform | 13010148297,16017538025,22012110426,22012111271 | Y | PASSED | aiyyapax
16017295838 | Verify sufficient MMIO space is available for different 32bit & 64bit POR devices that are connected to the SUT | BLOCKED | storage | bios.platform | bios.platform | 22015051481 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16014868604 | Verify system Boot successfully without any delay with 20 MB BIOS | PASSED | reset | bios.cpu_pm | bios.platform | 1509586924 | Y | PASSED | aiyyapax
14013173189 | Verify system Shutdown, Hibernate and Restart from OS via command Line | PASSED | power_management | bios.platform | bios.platform,fw.ifwi.pmc |  | Y | PASSED | mrajan2x
14013159055 | Verify system can Shutdown(S5) using "ALT+F4"' | PASSED | power_management | bios.platform | bios.platform | 22012112849 | Y | PASSED | agujjarx
14013173175 | Verify system can be Shutdown, Hibernate and Restart using "ALT+F4" key combination | PASSED | power_management | bios.platform | bios.platform |  | Y | PASSED | agujjarx
14013173176 | Verify system can be Shutdown, Hibernate and Restart using OS start menu | PASSED | power_management | bios.platform | bios.platform,fw.ifwi.others,fw.ifwi.pmc |  | Y | PASSED | agujjarx
14013173187 | Verify system can be cold reset and warm reset from EDK shell | PASSED | power_management | bios.platform | bios.platform | 15010556058,22014673903 | Y | PASSED | agujjarx
14013161178 | Verify system completes S4 Resume Cycles using "ResumeOK.efi" tool | FAILED | power_management | fw.ifwi.pmc | fw.ifwi.pmc |  | Y | FAILED | mrajan2x
14013173197 | Verify system entry and exit to Deep S4 and Deep S5 modes with system in AC mode | PASSED | power_management | bios.platform | bios.platform | 22012112780,22012113309,22012113328,22012113476 | Y | PASSED | bajanthx
14013121041 | Verify system exit from Connected Modern standby / S0i3 state via USB mouse | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012110173,22012110355,22012113290 | Y | PASSED | mrajan2x
14013115389 | Verify system stability after S4 and S5 cycles via power button | PASSED | power_management | bios.platform | bios.platform | 22012109249,22012110321,22012112805,22012112849,22012113067 | Y | PASSED | mrajan2x
14013157532 | Verify system stability on changing power state settings | PASSED | power_management | bios.platform | bios.platform | 13010638279,16013819216,16014213803,16018824655,22012113554,22012117865,22012118723 | Y | PASSED | mrajan2x
14013158271 | Verify system stability on performing Connected Modern Standby cycle pre and post Hibernate cycle | PASSED | power_management | bios.platform | bios.platform | 22012110173 | Y | PASSED | mrajan2x | Res pc10 : 99.44% , BIOSv_3162_01, IFWI 14.4
22011834694 | Verify system stability on performing Hibernate cycle on freshly preloaded OS post flashing Release BIOS | PASSED | power_management | bios.platform | bios.platform |  | Y | PASSED | bajanthx
14013173203 | Verify system stability on waking from idle state pre and post S4,S5 ,warm and cold reboot cycles | PASSED | power_management | bios.platform | bios.platform |  | Y | PASSED | bajanthx
14013182446 | Verify system stability post Sx and Deep S4 cycling with RTD3 option enabled in BIOS | BLOCKED | power_management | bios.platform | bios.platform |  | Y | BLOCKED | mrajan2x | other; CLID-10598
14013120979 | Verify system stability post Warm reboot cycles | PASSED | power_management | fw.ifwi.pmc | fw.ifwi.pmc | 15010556058,22012110302,22014673903 | Y | PASSED | mrajan2x
14013158146 | Verify system stability post applying workload on CPU | FAILED | power_management | bios.platform | bios.platform | 22012110356 | Y | FAILED | usavithx
14013158479 | Verify system state post flashing IFWI on an eSPI enabled system | PASSED | reset | bios.platform | bios.platform | 22012113786 | Y | PASSED | aiyyapax
14013158389 | Verify system wakes from CMS / S0i3 state successfully via USB Keyboard | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 22012110173,22012113278,22012113340 | Y | PASSED | mrajan2x
14013121133 | Verify system wakes from idle state successfully via Keyboard | PASSED | power_management | fw.ifwi.pmc | fw.ifwi.pmc | 22012110355 | Y | PASSED | mrajan2x
14013157006 | Verify that BIOS gives an option to change Tcc Activation Offset | PASSED | thermal_management | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | bajanthx
14013120501 | Verify that BIOS presents options to change the Boot Order | PASSED | reset | bios.platform | bios.platform |  | Y | PASSED | jmanigax
16018564232 | Verify that BIOS shall not set any TCC Offset programming | PASSED | thermal_management | bios.cpu_pm | bios.cpu_pm | 22015753765 | Y | PASSED | bajanthx
14013178190 | Verify that BIOS shall provide verb tables for HDA Config | PASSED | audio | bios.pch | bios.pch | 16013146685,16013867625,16014658928,16015119195,22012117860,22012118053,22016240366 | Y | PASSED | deivasix
14013177158 | Verify that CPU Attached Storage Device is Serviced by RST EFI Driver | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | usavithx
14013178784 | Verify that CPU Attached Storage Device is Serviced by RST EFI Driver Through VMD | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | aiyyapax
14013178789 | Verify that CPU Attached Storage Device list information in EFI shell Through VMD | PASSED | storage | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | aiyyapax
14013165616 | Verify that CPU north NPK related setup options are not present | PASSED | debug | bios.platform | bios.platform | 22012118048 | Y | PASSED | mrajan2x
14013156738 | Verify that Ctrl+P option should not displayed during SUT boot and should not enter into MEBx windows with ME Corporate SKU | PASSED | manageability | bios.me | bios.me,fw.ifwi.csme | 18014968941,22012119592 | Y | PASSED | sksharax
14013179310 | Verify that Debug Messages are sent over on Serial port with Debug BIOS | PASSED | reset | bios.platform | bios.platform,fw.ifwi.bios | 22012134474,22012691650 | Y | PASSED | aiyyapax
14013175760 | Verify that M.2 SSD device is functional without errors connected to M.2 socket connector | PASSED | storage | bios.pch | bios.pch |  | Y | PASSED | jmanigax
14013177211 | Verify that M.2 SSD device is functional without errors connected to M.2 socket connector | PASSED | storage | bios.cpu_pm | bios.cpu_pm,fw.ifwi.others,fw.ifwi.pmc |  | Y | PASSED | bajanthx
14013180258 | Verify that MEBx shall display an option to set the IP address and port number of the Intel AMT provisioning server | PASSED | manageability | bios.me | bios.me | 22012114065 | Y | PASSED | sksharax
14013175646 | Verify that Platform firmware Information is correctly displayed in BIOS setup | PASSED | system | bios.platform | bios.platform,fw.ifwi.bios | 22012110315,22012110361,22012111497,22012112077,22012112091,22012118951 | Y | PASSED | jmanigax
14013121695 | Verify that SUT boots to S0 from G3 in AC mode with AC brick | PASSED | power_management | bios.platform | bios.platform | 22012113429 | Y | PASSED | mrajan2x
14013175366 | Verify that the BIOS exposes VPU PEP option | PASSED | artificial_intelligence.vpu | bios.platform | bios.sa | 22012118300 | Y | PASSED | deivasix
14013173952 | Verify that the BIOS shall display the VBIOS/GOP version | PASSED | graphics | bios.sa | bios.sa | 16013816377,22012113046,22012118227,22012118546 | Y | PASSED | bajanthx
16012893578 | Verify the 'Global Reset Triggers' BIOS knob and functionality | BLOCKED | debug | bios.platform | bios.pch,bios.platform | 22012111105 | Y | BLOCKED | mrajan2x | other; CLID-6956
16019508897 | Verify the BIOS Version in the BIOS page | PASSED | reset | bios.cpu_pm | bios.cpu_pm,bios.platform | 22012113639 | Y | PASSED | aiyyapax
16019508973 | Verify the BIOS Version in the XML log matches with | PASSED | reset | bios.cpu_pm | bios.cpu_pm,bios.platform | 22012113639 | Y | PASSED | mrajan2x
14013166922 | Verify the BIOS first Boot time and Cold Boot time is inline with responsiveness metrics | PASSED | power_and_perf | bios.platform | bios.platform | 14017436111,16013366649,16017509475,22012117454,22012120328,22014194238,22015475726 | Y | PASSED | deivasix
16015633458 | Verify the Bios PCIe register details compared with BWG details using PCIe Utility tool from EFI shell | BLOCKED | io_pcie | bios.platform | bios.platform | 14013498769,14015154660,14016583253,14016593462,14016748439,14017226221,14017508449,14017513269,14017656131,14017793977,14017825783,14017825868,14017825883,14017894282,14017939232,14017997977,14018437567,14018889181,15011681684,15012591415,16012832810,16015457891,16016088104,16016632555,16017479883,16018675025,16018708944,16019108518,16019555271,16019727961,16020121467,16020289025,18025419078,18025419170,22012109429,22012115960,22012134532,22015180289,22015551380 | Y | BLOCKED | usavithx | other;
16013019950 | Verify the C states when SAGV enable/Disabled with MRC training | BLOCKED | memory | bios.mrc_client | bios.mrc_client | 14018821970,22012120981,22012636534 | Y | BLOCKED | deivasix | feature_not_yet_enabled; PC10 not asserting with debug
16013829771 | Verify the DMA Protected Range IMR1M implementation status | PASSED |  | bios.platform | bios.platform | 22012118263,22012118382 | Y | PASSED | bajanthx
16013835355 | Verify the Data stolen memory(DSM) IMR1M implementation status | PASSED |  | bios.platform | bios.platform | 16018669503,22012118263 | Y | PASSED | bajanthx
14013175476 | Verify the Dual Display functionality (onboard eDP+DP) in BIOS setup, EFI and OS | PASSED | display | bios.platform | bios.platform,fw.ifwi.bios | 16014646135,22012117393 | Y | PASSED | mrajan2x
16015167637 | Verify the Enumeration of PCIe device with PCIe option disabled in the Bios. | PASSED | storage | bios.platform | bios.platform | 14015273959 | Y | PASSED | aiyyapax
16013830759 | Verify the GTT stolen memory(GSM) IMR1M implementation status | PASSED |  | bios.platform | bios.platform | 22012118263 | Y | PASSED | bajanthx
16019340407 | Verify the Opportunistic Self Refresh knob in bios page | PASSED | memory | bios.mrc_client | bios.mrc_client | 14017015874 | Y | PASSED | sksharax
16012838549 | Verify the PCIe device Enable/Disable in Bios page | PASSED | storage | bios.platform | bios.mem_decode,bios.platform |  | Y | PASSED | aiyyapax
16016484527 | Verify the PCIe high MMIO IMR1M implementation status | PASSED |  | bios.platform | bios.sa | 22012118263 | Y | PASSED | bajanthx
14013160244 | Verify the SOL, USBr & KVM values in Smbios type 130 | PASSED | manageability | bios.platform | bios.me | 22012113821 | Y | PASSED | deivasix
16013836569 | Verify the TSEG IMR1M implementation status | PASSED |  | bios.platform | bios.platform | 22012118263 | Y | PASSED | bajanthx
16019380777 | Verify the boot to OS without any issues with Opportunistic Self Refresh enable and disable cross check with debug logs | PASSED | memory | bios.mrc_client | bios.mrc_client | 14017015874 | Y | PASSED | sksharax
14013160666 | Verify the correct ME Firmware version is displayed in the BIOS setup menu. | PASSED | manageability | bios.platform | bios.platform,fw.ifwi.csme |  | Y | PASSED | sksharax
16017269826 | Verify the detection of all the x1, x4,x8 SOC and IOE slots connected with LAN, External graphics card, NVMe PCIe devices | BLOCKED | io_pcie | bios.platform | bios.platform | 22012117875 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16019340053 | Verify the system boot to OS with safe loading bios enable knob enable/disable | PASSED | memory | bios.mrc_client | bios.mrc_client | 16015171718 | Y | PASSED | sksharax
14013184835 | Verify ucode firmware load/version check pre and post S3 cycle | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm,fw.ifwi.unknown | 14013763272,14013763785,14013763827,22012113584,22012118838 | Y | PASSED | mrajan2x
14013185500 | Verify ucode firmware loads pre and post S0i3 (Modern Standby) cycle | PASSED | processor_core | bios.platform | bios.platform,fw.ifwi.pmc | 22012113835 | Y | PASSED | mrajan2x
14013157460 | Verify user configured Power Limit 1 and Power Limit 2 values gets reflected correctly as part of PACKAGE_RAPL_LIMIT_0_0_0_MCHBAR_PCU MMIO regio | BLOCKED | power_management | bios.cpu_pm | bios.cpu_pm | 1509359566,1509366453,1509389728 | Y | BLOCKED | mrajan2x | awaiting_silicon; cTDP silicon is not available
14013157472 | Verify user configured Power Limit 4 values pre and post Sx cycles | PASSED | power_management | bios.cpu_pm | bios.cpu_pm | 16016360441,16018749958 | Y | PASSED | mrajan2x
14013180375 | Verify user is prompted for a new password and can"t use a non-strong password | PASSED | manageability | bios.me | bios.me | 22012113951,22012114006,22012114062 | Y | PASSED | sksharax
14013186947 | Verify user is prompted for a new password and can"t use a non-strong password' | PASSED | manageability | fw.ifwi.csme | bios.me,fw.ifwi.csme | 22012113951,22012114006,22012114062 | Y | PASSED | sksharax
14013185479 | Verify video playback in OS pre and post CMS/S0i3 cycle | PASSED | audio.cavs | bios.platform | bios.platform,fw.ifwi.bios,fw.ifwi.pmc |  | Y | PASSED | deivasix
14013177670 | Verify warm reset and Sx cycle with PCIe Gen3 NVMe SSD connected over PCIe Gen4 supported X4 slot | FAILED | storage | bios.pch | bios.pch,fw.ifwi.pmc | 22012117758 | Y | FAILED | jmanigax | CAT ERROR OBSERVED pci NVMe is connected to X4 slot
14013176011 | Verify xDCI option under USB configuratio | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012112213,22012112844,22012112884,22012113280,22012113776,22012115948,22012117350,22012120025,22012120027,22012620634 | Y | PASSED | deivasix
16016045588 | Verify xDCI option under USB configuration through EDK shell verificatio | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012112844,22012117350 | Y | BLOCKED | sksharax | other;
14013119320 | Verifying PCIe-USB add-on card support | PASSED | io_usb | bios.pch | bios.pch | 22012112479 | Y | PASSED | mrajan2x
14013173252 | [FSP2.0]: Validate FSP TempRamInit initialization and TempRamExit API"s | PASSED | system | bios.fsp | bios.cpu_pm,bios.me,bios.platform,bios.sa | 15010941533,16016835165,22012108345,22012112152,22012114353,22012120309 | Y | PASSED | jmanigax
14013173259 | [FSP2.0]: Validate Pre and Post OS display with different FSP Bios | PASSED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 15010171526,15010941533,22012108345,22012112152,22012114353,22012120309 | Y | PASSED | jmanigax
14013173257 | [FSP2.0]: Verify FSP Patch Table Information | PASSED | system | bios.fsp | bios.cpu_pm,bios.me,bios.platform,bios.sa | 15010171526,22012108345,22012112152,22012114353,22012120309 | Y | PASSED | jmanigax
14013173254 | [FSP2.0]: Verify FSP_INFO_EXTENDED_HEADER Information. | PASSED | system | bios.fsp | bios.cpu_pm,bios.me,bios.platform,bios.sa | 15010171526,22012108345,22012112152,22012114353,22012120309 | Y | PASSED | jmanigax
14013173249 | [FSP2.0]: Verify FSP_INFO_HEADER Information | PASSED | system | bios.fsp | bios.cpu_pm,bios.me,bios.platform,bios.sa | 15010171526,15011455229,16016660102,16017268940,22012108345,22012112152,22012114353,22012120309 | Y | PASSED | jmanigax
14013173289 | [FSP] Verify FSP BIOS Dispatch mode Boot Flow | PASSED | system | bios.fsp | bios.cpu_pm | 15010941533,16016660102,22012108345,22012249339,22015439406 | Y | PASSED | jmanigax
14013173279 | [FSP] Verify FSP Header File(.fd) and boot setting file(.bsf) loads correctly into BCT tool | BLOCKED | system | bios.fsp | bios.cpu_pm |  | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013161309 | [FSP] Verify SX transition of the system with FSP VS build | PASSED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 22012109271 | Y | PASSED | jmanigax
14013173339 | [FSP] [GCC]Verify SX transition of the system with FSP GCC Release build | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform |  | Y | FAILED | jmanigax
14013173326 | [FSP][GCC] Verify FSP BIOS Dispatch/API mode Boot Flow | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 15010941533,16015253989,16016660102,22012108345,22012249339,22015439406 | Y | FAILED | jmanigax
14013173347 | [FSP][GCC]: Validate FSP TempRamInit initialization and TempRamExit API"s | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 16016835165,22012112152,22012114353 | Y | FAILED | jmanigax
14013173307 | [FSP][GCC]: Validate Pre and Post OS display with different FSP Bios | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 15010941533,22012109271,22012112152,22012114353 | Y | FAILED | jmanigax
14013173311 | [FSP][GCC]: Verify FSP Patch Table Information | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 22012109271,22012112152,22012114353 | Y | FAILED | jmanigax
14013173313 | [FSP][GCC]: Verify FSP image ID and Image Revision | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 16017268940,16018410112,22012109271,22012112152,22012114353 | Y | FAILED | jmanigax
14013173351 | [FSP][GCC]: Verify FSP_INFO_EXTENDED_HEADER Information. | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 22012112152,22012114353 | Y | FAILED | jmanigax
14013173341 | [FSP][GCC]: Verify FSP_INFO_HEADER Information | FAILED | system | bios.fsp | bios.cpu_pm,bios.fsp,bios.platform | 15011455229,16015727596,16016660102,16017268940,22012112152,22012114353 | Y | FAILED | jmanigax
14013165608 | [Hybrid] Verify system stability post Connected Modern Standby when only Atom or BIG cores are individually enabled | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm | 22012110519 | Y | PASSED | deivasix
14013157608 | [Hybrid]Verify 3D benchmark tool on Hybrid Processor When Big and Small Cores are enabled | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157616 | [Hybrid]Verify 3D benchmark tool on Hybrid Processor When Big and Small core is Enabled and Hyper-Threading is Disabled | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157613 | [Hybrid]Verify 3D benchmark tool on Hybrid Processor When Big is Disabled/1 and Small Cores is Enabled | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157611 | [Hybrid]Verify 3D benchmark tool on Hybrid Processor When Big is enabled and Small Cores is disabled | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013157614 | [Hybrid]Verify core and thread in BIOS/EFI , when core 1 is enabled | PASSED | processor_core | bios.cpu_pm | bios.cpu_pm |  | Y | PASSED | deivasix
14013181906 | [Ingredient NIC] - PreAlpha - Verify system can perform 10 S4 cycles | PASSED | power_management | bios.platform | bios.platform | 15012890449 | Y | PASSED | mrajan2x | verified with ICT tool
14013181927 | [Ingredient NIC] - PreAlpha - Verify system can perform 10 S5 (Cold Reboot) cycles | PASSED | power_management | bios.platform | bios.platform |  | Y | PASSED | mrajan2x
14013181910 | [Ingredient NIC] - PreAlpha - Verify system can perform 10 S5 (Warm Reboot) cycles | PASSED | power_management | bios.platform | bios.platform |  | Y | PASSED | mrajan2x | veriifed with ICT tool
16019509672 | [Negative] Verify Xml Cli support when BIOS is option disabled | PASSED | reset | bios.platform | bios.platform | 16013381910 | Y | PASSED | aiyyapax
16016730107 | [Negative] verify WRC feature support from Bios | PASSED | reset | bios.sa | bios.sa | 22012117959 | Y | PASSED | aiyyapax
14013164543 | [OCR] Verify AMT triggered HTTPS Boot Flow over wired LAN | FAILED | manageability | bios.me | bios.me,fw.ifwi.csme | 22012116471 | Y | FAILED | bajanthx
14013164519 | [OCR] Verify AMT triggered PBA Boot Flow over wired LAN | FAILED | manageability | bios.me | bios.me,fw.ifwi.csme | 22012113735,22012115684 | Y | FAILED | bajanthx
16018974363 | [OCR] Verify HTTPS Boot flow for One Click Recovery over HTTPS Proxy Support after G3 state | FAILED | manageability | bios.platform | bios.platform | 22012116466 | Y | FAILED | bajanthx
16018964330 | [OCR] Verify HTTPS Boot flow for One Click Recovery over HTTPS Proxy Support after S4 cycle | FAILED | manageability | bios.platform | bios.platform | 22012116466 | Y | FAILED | bajanthx
14013164625 | [OCR] Verify OCR progress and state via AMT Event log for HTTPS Boot over wired LAN | FAILED | manageability | bios.me | bios.me | 22012117332 | Y | FAILED | bajanthx
14013165106 | [OCR] Verify Remote Power Command after performing OCR_WinRE Boot flow | FAILED | manageability | bios.me | bios.me,fw.ifwi.csme | 22012114035 | Y | FAILED | usavithx
14013159248 | [TBT] Verify DP display functionality on hot-plug and after Sx states over TBT port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012119668,22012120025,22012120027,22012120032 | Y | PASSED | deivasix
14013159022 | [TBT] Verify SUT wake from S3/S4 using TBT-Dock connected over TBT port | BLOCKED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 14017767022,22012111480,22012113350,22012119668,22012120032,22012133075 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
14013159024 | [TBT] Verify SUT wake from S3/S4 using Type-C dock connected over TBT port | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa | 22012111480,22012113350,22012119668,22012120032,22012133075 | Y | PASSED | deivasix
14013185200 | [TBT] Verify Thunderbolt Add in Card Enumeration in device manager | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sphy,fw.ifwi.tbt |  | Y | PASSED | mrajan2x
14013184477 | [TBT] Verify Thunderbolt Enumeration in device manager | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.nphy,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.sphy,fw.ifwi.tbt |  | Y | PASSED | mrajan2x
14013159129 | [TBT] Verify USB 2 Device functionality in Host Router before/after Sx cycles | PASSED | io_usb.type_c_subsystem | bios.platform | bios.platform,bios.sa,fw.ifwi.MGPhy,fw.ifwi.dekelPhy,fw.ifwi.iom,fw.ifwi.pmc,fw.ifwi.sam,fw.ifwi.tbt |  | Y | PASSED | deivasix
16014621255 | verify BIOS trace capabilities between Serial and NPK | BLOCKED | debug | bios.pch | bios.pch | 18017104530 | Y | BLOCKED | mrajan2x | other;
16017999538 | verify MemSS_PMA_CR_FLOW_STATUS via debug log. | PASSED | memory | bios.platform | bios.platform | 14016201693 | Y | PASSED | sksharax | Verified with available Slots
16015889071 | verify PCIe EQCFG1 LEB register | PASSED | io_pcie | bios.platform | bios.pch,bios.platform | 14015415848 | Y | PASSED | bajanthx
16017829295 | verify PCIe register RXL0SEG12FTSE using PythonSV | BLOCKED | io_pcie | bios.platform | bios.platform |  | Y | BLOCKED | mrajan2x | other; TC ID is invalid,need to raise clarification
16017961115 | verify PCIe sub option for SOC , IOE and PCH configuration | BLOCKED | io_pcie | bios.platform | bios.platform | 14016132853,14017160047,16015276168,22012112954,22012112954,22012113685,22012117473,22012118484,22015074549 | Y | BLOCKED | bajanthx | feature_not_yet_enabled;
16016996199 | verify Peripheral channel register from SOC and PCH | PASSED | io_general | bios.platform | bios.platform | 16015085284 | Y | PASSED | mrajan2x
16018723453 | verify and make sure that BIOS setup option Crashlog Storage Off is disabled by default for MTL-S A0, and MTL-MP B0 steppings | PASSED | debug | bios.platform | bios.platform | 22015774517 | Y | PASSED | mrajan2x
16017097395 | verify the NVMe SSDs detection on the all M.2 available ports from SOC and IOE | PASSED | storage | bios.platform | bios.platform |  | Y | PASSED | jmanigax